GRANT  Application.

Angira Community Home Based Care Organization

Grant Application

Section 1: Contact Information

Name of Organization (including acronym if there is one) Angira community home based care

When was the organization established?  2009 and registered as a CBO in 2010

Name of Contact Person:   Alfred Onyango Nyakwaka  	Title: Executive Team leader

Phone (including country and city code) +254, 0710 - 681467

Fax -__________	 		Email: alub20@yahoo.com

Mailing address of the organization

Town Kisumu 		Country Kenya	 Postal Code 40103

Physical address of the organization (if different from above) _The same

Town Kisumu 		Country Kenya	 Postal Code 40103

Bank name; KCB Kisumu

Account Title;  Angira  CBO

Account number;  1122728549

Website address _Not available currently___________________________________

Section 2: Background Information

Type of organization:

Community-based organization (CBO)

Organization Vision:

A full life for all the children

Organization’s mission:

Our mission is to develop, promote and/or  support community systems that reduce cycle of orphaned and vulnerable children and those that facilitate the realization of their full potential in life.

Brief history of organization:

The idea of Angira Community Home Based Care Organization arose after the founder and the current Chairman Mr. Alfred Onyango Nyakwaka in 2007 at around 10.00am, saw a little boy of around nine years of age sneaking out a fence with a bunch of bananas in Kajulu Village of Kisumu.  He stealthily followed the boy and saw him enter a grass thatched house a few meters away with the bananas.  He realized that the boy may have stolen the bananas to feed his family and was greatly disturbed.  He proceeds to his workplace but later in the evening visited the house where he saw the boy entering.  He met an ailing old lady, the boy he had spotted, plus three other younger children.  He introduced himself as a neighbor and the lady narrated how the children had to drop out of school to help her fend for the family.   He gave them the supplies he bought in town and since then started supporting them with the understanding the children must resume school immediately.  He purchased their uniform and re-enrolled them in school.

Mr Nyakwaka realized that there are many more children facing the same plight and recruited three more but soon realized that his meager resources could not support all of them, and therefore he would go around soliciting funds from his neighbors, friends and the local church to help him support these destitute children.

In April 2009 he brought together ten men and women from the community, who had also been seriously touched to form the Angira  Human development organization.  The aim of the  organization was to support the orphaned and vulnerable children in the community lead better lives and go back to school.  As the organization sought registration this year it was advised to change the name to Angira Community Home Based Care Organization.

Main objectives of the organization

- To provide reasonable shelter and other basic needs to resource poor and other vulnerable children

- To facilitate the education and training of poor orphans and other vulnerable children.

- To promote hygiene and healthy living among the families of the poor orphaned and other vulnerable children.

- To conduct programmes that reduces the incidence and prevalence of orphans and vulnerable children within the community.

Who are the key target groups your organization assists?

- Orphans

- Vulnerable children

- Caretakers of orphans and vulnerable children

Describe current programs and activities

Currently the project activities are hinged on rescuing orphans and vulnerable children who have dropped out of school.  The program supports the children in buying their books, uniforms and paying fees.  The project has been supporting the child caretakers by supplementing on their foods, clothing and beddings.  The Project staff have been dedicated in counseling the children. They have also been keen on creating awareness of HIV/AIDS and provide Home based care to the sickling.

Describe organizational accomplishments

- 14 who dropped out of school have been returned to school are learning.

- OVC’s families have been supported with food and other basic necessities

- The Children is visited and her work in school boosted with extra tuition.

- Over 20 OVC care givers have been encouraged and gone HIV/AIDS counseling and testing.  Some have joined post-test clubs

How does the organization fund its activities?

1.  Member subscriptions and contribution.

2   Through Personal donations

3.  Fund Raising (Harambee)

4.  Voluntary work

5. Government food grants

What is the total annual income of the organization from self-funded, local, government, or international sources?

(Average the last three years, in U.S. dollars)?

1.  Self funded  - 		US $20,000

2.  local  sources -		US $10,000

3.  Government,- 		US $  2,000

4.  International sources -	US $ 0

Describe the structure of the organization, including the governing body, trustees, or management structure, and number of staff (paid and/or volunteers)

Annual General Meeting (AGM) of Members - This is the highest decision making body in the organization.  The powers of this body are only exercised in the duly constituted meetings.  The  AGM is conducted once a year but Special General Meeting (SGM) may be held at any time to thrash out any critical issues at hand.  There are currently 15 members of Community Based organization (CBO).  The main functions of the AGM are to approve annual reports and budgets.  The body has also the authority of electing all the organization officials.

Management Committee - This body consist of 5 persons, 3 males and 2 females.  The main business of the management committee is to develop policies and implement organizational programs.  This body is headed by a chairman.  The Team leader is the sectary to the committee and is an executive.

Trustees - These consist of three members.  All the property of the organization is vested on the trustees.  This board has the duty and obligations of securing the organization's assets  and property.  They are answerable directly to the members.

Organization's Staff - The organization staff is headed by a Team Leader who is also the secretary to the board.  Currently the organization does not have any paid regular staff and depends on the voluntary services of officials, members and other well wishers.  There are different  committee member as  HIV/AIDS and home based care coordinator, the Nutrition coordinator and education sectary.  The organization gets a regular services from a Technical advisor at highly subsidized rates.

Describe any major projects that have been carried out by your organization in the last two years

The organization’s only project is the Child Empowerment Project.  This has been limited to rescuing OVC, supporting their education and taking care of them.  It also has the component of HIV/AIDS awareness.

Section 3

Has your organization received previous funding from any international org?

No

How do you find out about Org,?

_From a partner/donor _√ Internet (search engine) _ Media _ Other (please specify)

____________________________________________________________________________

Section 4: Specifics About Your Project

Name of proposed project _____Angira Orphans Community Support Project

Amount of funding request _______US $ 794,310.12____________________

Location of the project (stipulate country, district, and town/village)

Kenya, Nyanza Province, Kisumu East District, Winam division, East Kajulu Location.

Why was this area chosen for your project?

The area was chosen because it is one of the locations with the highest number of orphans and is also where the founder member lives and started the project.  The area has an HIV/AIDS prevalence of over 14 %( Kenya Population Census, 2007)

Provide evidence of the need in this community

More than 15 % of the children who live in the location are either vulnerable or orphaned.  The average income of the area is less than I dollar a day, ie. Poverty levels are very high in the area.  HIV/AIDS prevalence in the district is more than 14% and has not reduced substantially in the last five years

Describe the category of your project:

_ Health of orphaned children _ Safety of orphaned children _√ Care of orphaned children

√_ Education of orphaned children _√ Preventative Educational/Health community program

Approximate numbers (gender, age, and other relevant categorization)

| Category | Male | Female | Total |
| --- | --- | --- | --- |
| Total orphaned Children | 67 | 89 | 156 |
| Partial orphaned Children | 123 | 176 | 299 |
| Other Vulnerable Children | 219 | 434 | 653 |
| TOTAL | 409 | 699 | 1,108 |

Please describe the nature of your project.

The Project seeks to work with community members to be supportive of the need of the orphaned and vulnerable children.  It is an integrated Project and has the following Key components._

- Community awareness and Prevention of HIV/AIDS

- Building of Orphanage and rescue centre.

- Care and education of orphaned & vulnerable children.

- Revenue generation Activities to sustain the core project activities.

What is the anticipated length of your project?

This is a long term Project.  It is proposed that the project be funded for three years and after that it should be sustaining.

What is the project’s overall objective?

To reduce the prevalence of OVC in the community and to support the OVCs to realize their life potentials in full

Discuss the issue/need to be addressed by the project?

The project will address the following issues:

- Prevalence of orphaned children in the area especially those arising from sicknesses death caused by HIV/AIDS.

- Poor care of orphaned and vulnerable children.

- School drop-out rates, low school level transitional rate  and juvenile delinquency among orphaned and vulnerable children

- Sustainability of the project

What change is the project hoping to achieve?

The project is hoping.

- To reduce the numbers of orphaned children

- To improve the living standards of orphaned and vulnerable children

- To increase the school retention rate among orphans

- To increase the transition educational transition from primary school to secondary among orphans and vulnerable children by at least 5%.

- To improve the average income among OVC caregivers  in the area

What are the potential difficulties, limitations, or anticipated problems?

Funds – the projects will require huge amounts of money to build an orphanage and run the other components of the project.  This  money is not at hand.

Personnel/staff - The Project requires dedicated and knowledge staff.  The capacity of the current level of staff may need to be increased as the project will become more complex as it evolves.

Cooperation from the community - The achievement of the project outcome and purposes can only be achieved by their cooperation.  There are some extraneous factors which may comprise their cooperation

Discuss the measures that will be taken to overcome them

Finances – Fundraising activities will be conducted both locally and abroad.  In the long run revenue generating activities (RGA’s) will be organized at the community level to support OVC care givers and reduce the OVC’s dependence on the project funds.  At the organizations level ,the RGA will be conducted to support the recurrent expenditure and to make the activities sustainable.

Personnel/staff – The Project will use both salaried and voluntary staff.  It is the policy of the Project local persons from the community in as much as possible and improves their capacity as much as possible.  Only where technical skills are required will salaried staff from outside the community be employed.  This is expected to translate in reduced wage bill and at the same time not comprising efficiency and effectiveness.   Volunteers from all over the world will be highly encouraged.

Cooperation from the community – The community has been involved and will continue to be involved at all stages of the project.  They  will enhance ownership, contribution, Knowledge and thus reduce resistance to change in behaviour. _______________

How does this project advance any organization goals set out in its mission statement?

The Project will advance Orphans’ Heroes’ goals set out in its mission statement by developing and supporting community institutions and systems that facilitate the care and education of orphans.  It will also help break the cycle of factors that create orphans.

Is this an existing or ongoing project? _√ yes _ no If yes, please describes the project to date. Describe the outcomes and current state of the project, any improvements in the proposed project, and the measurable outcome that will be achieved during the funding period.

Currently the project focuses on rescuing orphans and vulnerable children and supporting their nutritional and basic needs at home.  The project has been able to return and retention 14 children at Primary school level.

During the funding period the project intends to support up to 100 OVC, sheltering those who do not have caretakers the expected orphanage and office centre to be built.  The centre will host the children; provide organizational offices and hall used for various activities as extra tuition.

The project will also improve on the educational support to now include not only buying uniforms but also payment of books and extra tuition where deemed necessary.  Another development will see Angira CHBCO facilitating OVC school transition by also supporting OVC’s in Secondary Schools and vocational institutions.  Currently no child in secondary school has ever been supported by the project.

The Project will now work with peer educators and nearby health facilities to mobilize community members to go for HIV/AIDS counseling and testing, thus increasing the number of men and women who know their status.   The peer educators will also educate the community members on family planning, the benefits and methods to be used.  This component is expected to result in reduced number of children exposed becoming either orphans or vulnerable.

The project is also expected to go a long way to improving its own sustainability by initiating and running Income Generating Activities at the organizational and community levels.  The use of capacity building and revolving funds to facilitate the OVC care takers to run   their own business, and thus generate their own income to fend for the OVC’s under their care.  This will reduce the level of dependency of the OVC’s on the Project.  The Project IGA’s namely through outside catering, hiring of facilities will provide funds to run the centre and its programmes.

Is this a new project? _ yes _√ no.  If yes, please describe how the project approach was developed and how the project will be implemented.

___________N/A________________________________________________________________

Section 5: Volunteer/Donor/Staff Participation in Your Project

Will other organizations be involved in this project? _√ yes _ no if yes, please list the names of the organization and how it will be involved.

The Government through the social services department and children’s department – They collaborate and participate in facilitation of trainings.

Local Hospitals – Providing HIV/AIDS counseling and testing.

Millpath Development consultants – Technical advice, capacity building and M&E

Provide a brief biographical sketch of all personnel involved in this project.

Alfred Onyango Nyakwaka – Is the founder  chairman of the organization.  He is 35 years old and social worker and business man by occupation.  He has worked in the Mission for Africa (MFA) children Home on Voluntary basis for more than 2 years.  Previously he worked with United Church of Africa as a project coordinator in charge of the Street children project.  He also runs a small business in town.

Risper J. Omondi  is the treasurer is the CBO.  She is 34 years old and is a professional teacher.  She is a staunch Christian and has served in various capacities in the church including treasurer of the catholic mission church within the local community. Between the years 2006 to 2008.  She is currently living with and supporting six orphans.

Emily L. Akoth is aged 30 is currently working as a technologist Researcher at Centre for Disease control in Kisumu.  Between 2007 and 2009 she worked with International medical Corps in humanitarian areas within the country and 2003 – 2005 CDC on HIV/AIDS Project.  She is the secretary to the organization

How many participants will be chosen or recruited for this project, if applicable?

100 OVC’s

Will there be any participant fees? _ Yes _√ no.  If yes, please describe

Section 6: Measurable Results of Your Project

Discuss any similar projects being implemented by other entities and how this project differs.

There are  orphanages but  outside the district.  These orphanages only recruit orphans care for them.  They do not involve the communities in their activities and contribute to breaking the cycle that causes orphans.  This project will endeavor to break these new grounds.

Describe the measurable outcome that will be achieved during the funding period.

- Organizational office and orphanage built.

- 100 Orphaned child placed at orphanage or with Care takers.

- Community Awareness on HIV/AIDS built.

- Number  of community members who know their status increased.

- IGA  started and running  the project at community level – increased

- OVCs’ given educational support.

What are the measurable long-term outcomes of this project?

- Level of orphan prevalence reduced by over 20%

- Increased  OVC  school retention rates by 100%

- Increased  OVC  school transitional rates  by at least 90%

- Improvement  in standard of living of OVC’s and their families

What methods/strategies will be used to gather data on and evaluate the project?

Participatory data collection (PRA/PLA ) and analytical techniques.  An external evaluator too, will be engaged to design the system to improve objectivity

How will the project evaluation be used?

- To redesigning and improve the project strategies.

- To inform the organization and stakeholders of the status project.

- For control purposes – realign deviations

- To ascertain to what extent to which the project purpose and goals have been achieved for replication.

Progress reports will be expected to ensure that funds are being used appropriately. The schedule of progress reports depends upon the project's length and will be established on a case-by-case basis. The org funding the projects will visit at any time. Will you comply with the schedule of progress reports outlined by any funding Org, and share your data with that funding org? _√ yes _ no

Section 7: Budget/Schedule of Project

In addition to the questions below, please submit a detailed (two pages maximum) budget attached to this application. List all revenue and expenses for this project, being very specific. for expenses, be sure to detail all direct and indirect expenses. For revenue, list all funding acquired for this project and all outstanding funding requests.

What is the total budget for this project? ______ $794,310.12______________________________

How much funding are you requesting from volunteer org? $589,001.31

List other funding resources you have already secured for this project

From Angira’s HBC organization members – donations, voluntary work, fundraising, IGA and contributions in kind.

What resources will be needed to sustain this project over time?

Resources to conduct OVC care and Education approximately $ 164,192.57 for the first three years.

How will these resources be secured?

Through conduct of IGA’s at both organization level and community level

Outline the schedule of work for this project (what will be accomplished, and by when).

Is there any additional information you would like to provide about the budget or schedule?

_√ yes _ no

There budget notes are in the excel worksheets. Child Proposal Budget.xlsx

Section 8: References

Please supply the following information for two external references (e.g. donors, volunteers, director of another organization).

REFERENCE #1

Name _James   Otieno______________________ Email: angiradev.ce@hotmail.co.uk

Organization and job title _______St Johns Ambulance. Program director

Phone (including country and city code) ______+244723956649______________________________________

How does this person know the organization?

He have been in close contact and visited the organization.  Are currently considering creating Aids awareness for the organization

How long has he/she known this organization? _______6 months______________

REFERENCE #2

Name ___Pius Asaka Nyangara _________________________ Email: asakanyangara@wfp.org

Organization and job title World Food Programme – Thailand Coordinator

Phone (including country and city code) ____+668 47728120___________

How does this person know the organization?

Has known the founder for sometime.  Recently visited the project while in vacation

How long has he/she known this organization? _______6 months______________

Please be sure to attach a detailed budget for your proposed project. Do not attach any other unrequested materials.

I ensure that all of the information provided in this application is complete and accurate.

________________________________			17th November.2010__

Signature						Date

_______ Alfred Onyango Nyakwaka ___

Print Name