Total Project cost and Activity Planning of Diabetic Retinopathy Awareness and Treatment Project of Drashti Netralaya:

| A | Activity | Output | Probable time frame |
| --- | --- | --- | --- |
|  | Printing Handbills | Awareness | Starting and at starting of each outreach camp |
|  | Printing Wall Posters-Hindi+Gujarati | Awareness | Starting and 6 month |
|  | Printing Broachers-English | Awareness of medical and paramedical personnel | Starting (2nd month) |
|  | Printing Referral Slips | Referral network documentation | Starting |
|  | Printing Camp Case paper | Camp registration and documentation | Before first outreach |
|  | Printing Proforma-fully examined and registered case | Medical Record document | Starting-as general outdoor referred cases screening started |
|  | Treatment Sheet | Document treatment details | Starting and continued |
| B | Meetings |  |  |
|  | General Practitioners-1 | Education and awareness | starting |
|  | General Practitioners-2 | Education and awareness | After 4 months |
|  | General Practitioners-3 | Education and awareness | After 9 months |
|  | Pharmacist-1 | Education and awareness | Starting |
|  | Pharmacist-2 | Education and awareness | After 6 months |
|  | Lab technicians-1 | Education and awareness | Starting |
|  | Lab technicians-2 | Education and awareness | After 6 months |
|  | Public | Education and awareness | continuous |
| C | Outreach activity |  |  |
|  | Outreach Mobile Visit-1 On mobile van with telemedicine connectivity | Diabetic and Diabetic retinopathy screening |  |
|  | Outreach Mobile Visit-2 On mobile van with telemedicine connectivity at BOU | Diabetic and Diabetic retinopathy screening |  |
|  | Outreach screening Visit-3 Opportunistic screening | Diabetic and Diabetic retinopathy screening |  |
| D | Hospital Activity |  |  |
|  | Screening | To detect +nce and note type of problem | Regularly |
|  | Investigation-Fundus Fluoresceine Angiography, sonography, Fundus photography | To determine regarding type of treatment. | Regularly |
|  | Laser Treatment | Treatment | Regularly |
|  | Follow up and investigations | For detection of recurrence and completion of treatment | Regularly |
|  | Surgery | To treat complicated cases. | Regularly |
| E | PR |  |  |
|  | News Paper ad-general edition | Propaganda for outreach+education and awarness | Twice - yearly |
|  | News Paper ad-local edition | Propaganda for education and awareness+education and awarness | With outreach camp |
|  | Periodical as local | Propaganda for education and awareness+education and awarness | As and when necessary according to out reach camps |
| F | Evaluation | To assess impact | End of 3rd year |

|  | Activity | Output | Probable time frame | Months of year [starting at any month] Color indicates the month/s in which the activity will be organised. |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 |  | 9 | 10 | 11 | 12 |  |
| 1 | Printing Handbills | Awareness | Starting & At each outreach camps |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Printing Wall Posters-Hindi+Gujarati | Awareness | Starting & 6 month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Printing Broachers-English | Awareness of medical and paramedical personnel | Starting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Printing Referral Slips | Referral network documentation | Starting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Printing Camp Case paper | Camp registration and documentation | Starting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Printing Proforma-fully examined and registered case | Medical Record document | Starting-as general outdoor referred ……. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Treatment Sheet | Document treatment details | Starting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Meetings |  |  |  |  |  |
| 8 | General Practitioners-1 | Education and awareness | First |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | General Practitioners-2 | Education and awareness | After 4 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 10 | General Practitioners-3 | Education and awareness | After 9 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 11 | Pharmacist-1 | Education and awareness | Second |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 12 | Pharmacist-2 | Education and awareness | After 6 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 13 | Lab technicians-1 | Education and awareness | First |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 14 | Lab technicians-2 | Education and awareness | After 3 months |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 15 | Public Awareness | Education and awareness | Regularly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Outreach activity |  |  |  |  |  |
| 16 | Outreach Mobile Visit-1 On mobile van with telemedicine connectivity | Diabetic and Diabetic retinopathy screening | Every month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 17 | Outreach Mobile Visit-2 On mobile van with telemedicine connectivity at BOU | Diabetic and Diabetic retinopathy screening |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 18 | Outreach screening Visit-3 Opportunistic screening | Diabetic and Diabetic retinopathy screening |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  |  |  |  |  |  |  |  |  |  |  | Hospital Activity |  |  |  |  |  |
| 19 | Screening | To detect +nce and note type of problem | Regularly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 24 | Project manager salary | To report and monitoring | Regularly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 25 | News Paper AD-General edition Gujarati/Hindi/English | Education and awareness | Starting 6th month |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 26 | News Paper ad-local | Education and awareness | With outreach camp |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 27 | Periodical ad-local | Education and awareness | With outreach camp |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 28 | Evaluation |  | End of project |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Activity |  |  | Output | Probable time frame | Units in 1 year | Other expenses if any | Other expenses if any | Other expenses if any | Rate/Unit |  | Total expense |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Printing Handbills |  |  | Awareness | Monthly | 12 |  |  |  | 1000 |  | 12000 |
| 2 | Printing Wall Posters- Hindi +Gujarati |  |  | Awareness | 2 times in yr | 2 |  |  |  | 25000 |  | 50000 |
| 3 | Exhibition posters with Lamination |  |  | Awareness | Monthly | 1 |  |  |  | 25000 |  | 25000 |
| 4 | Printing Broachers-English |  |  | Awareness of medical and paramedical personnel | Starting | 1 |  |  |  | 25000 |  | 25000 |
| 5 | Printing Referral Slips |  |  | Referral network documentation | Starting | 200 |  |  |  | 15 |  | 3000 |
| 6 | Printing Camp Case paper |  |  | Camp registration and documentation | Before first outreach | 50 |  |  |  | 100 |  | 5000 |
| 7 | Printing Performa-fully examined and registered case |  |  | Medical Record document | Starting-as general outdoor referred cases screening started | 25 |  |  |  | 1000 |  | 25000 |
| 8 | Treatment Sheet |  |  | Document treatment details | Starting | 5 |  |  |  | 300 |  | 1500 |
| 9 | News Paper AD-General edition Gujarati/Hindi/English |  |  | Education and awareness | First month Sixth month | 2 |  |  |  | 10000 |  | 20000 |
| 10 | News Paper ad-local |  |  | Education and awareness | With out reach camps | 12 |  |  |  | 5000 |  | 60000 |
| 11 | Periodical ad-local |  |  | Education and awareness | With outreach camps | 12 |  |  |  | 1000 |  | 12000 |
| 12 | Computer and office |  |  | once | Once | 3 |  |  |  | 25000 |  | 75000 |
|  | Evaluation |  |  |  |  |  |  |  |  |  |  | 50000 |
|  | Subtotal |  |  |  |  |  |  |  |  |  |  | 363500 |
|  | Meetings |  |  | Output | Probable time frame | Units in 1 year | No of participants | Fooding expense | Others [Stationary etc] | Expense/Unit |  | Total expense |
| 13 | General Practitioners-1 |  |  | Education and awareness | Quarterly | 4 | 15*4 | 20000 | 2000 | 7500 |  | 22000 |
| 14 | Pharmacist-1 |  |  | Education and awareness | Quarterly | 2 | 15*2 | 10000 | 2000 | 7500 |  | 11000 |
| 15 | Lab technicians-1 |  |  | Education and awareness | 6 monthly | 2 | 10*2 | 10000 | 2000 | 5500 |  | 11000 |
| 16 | Public |  |  | Education and awareness | Regularly | 4 | 100*4 | 16000 | 2000 | 4500 |  | 18000 |
|  |  |  |  |  |  |  |  |  |  |  |  | 62000 |
|  | Outreach activity |  |  |  |  | Units in 1 year | Travel expense | Other expense if any | Other expense if any(staff) | Expense/Unit |  | Total expense |
|  | Outreach Mobile Visit-1 On mobile van with telemedicine connectivity |  |  | Diabetic and Diabetic retinopathy screening | Every month | 12 | 5000 | 5000 | 5000 | 15000 |  | 300000 |
|  | Outreach Mobile Visit-2 On mobile van with telemedicine connectivity at BOU |  |  | Diabetic and Diabetic retinopathy screening | Every month | 6 | 5000 | 5000 | 5000 | 15000 |  | 150000 |
|  | Outreach screening Visit-3 Opportunistic screening |  |  | Diabetic and Diabetic retinopathy screening | Quarterly | 4 | 5000 | 5000 | 5000 | 15000 |  | 60000 |
|  |  | SUB TOTAL Rs. |  |  |  |  |  |  |  |  |  | 510000 |
|  | Hospital Activity |  |  | Output | Probable time frame | Units in 1 year | Cost /Unit | Other expenses if any | Other expenses if any | Other expenses if any |  | Total expense |
|  | Screening |  |  | To detect +nce and note type of problem | Regularly | 240 | 50 |  |  |  |  | 12000 |
|  | Investigation-Fundus Fluoresceine Angiography, sonography, Fundus photography |  |  | To determine regarding type of treatment. | Regularly | 50 | 250 |  |  |  |  | 12500 |
|  | Laser Treatment |  |  | Treatment | Regularly | 100 | 500 |  |  |  |  | 50000 |
|  | Follow up and investigations |  |  | For detection of recurrence and completion of treatment | Regularly | 50 | 250 |  |  |  |  | 12500 |
|  | Surgery |  |  | To treat complicated cases. | Regularly | 12 | 10000 |  |  |  |  | 120000 |
|  | Project manager salary |  |  | To facilitate reporting and monitoring of project | 1 yr | 12 | 10000 |  |  |  |  | 120000 |
|  | Data entry operator(part time) |  |  | To maintain and update data | 1 year | 12 | 4000 |  |  |  |  | 48000 |
|  |  |  | SUB TOTAL Rs. |  |  |  |  |  |  |  |  | 375000 |
|  |  |  | GRAND TOTAL Rs. INR |  |  |  |  |  |  |  |  | 1310500 |

| No | Equipment | Cost |
| --- | --- | --- |
| 1 | NMFA | 1500000 |
| 2 | OCT | Other source -2925000 |
| 3 | Operating Microscope-Zeiss lumera | Other source -3500000 |
| 4 | Up gradation of Vitrectomy consol | Other source-3600000 |
|  | Total INR | 12100000 |

Communication Equipments:

| No | Communication Equipment | Cost |
| --- | --- | --- |
| 1 | Computer-2 | 70000 |
| 2 | Data Cards-3 | 6000 |
| 3 | Software-5 users(C-DAC) | 50000 |
|  | Total INR | 126000 |

Recurring cost:

| No | Communication recurring Item | Cost | Total/year |
| --- | --- | --- | --- |
| 1 | Recurring connectivity cost | 10000/month | 120000 |
| 2 | Internet Data Cards-3 | 2000/month | 24000 |
|  | tOTAL | INR | 144000 |

|  | Activity | Output | Probable time frame | Months of year [starting at any month] State the expenditure in the months for the activities. |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | TOTAL Expense |
| 1 | Printing Handbills | Awareness | Starting | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 1000 | 12000 |
| 2 | Printing Wall Posters-Hindi+Gujarati | Awareness | Starting |  | 25000 |  |  |  |  |  | 25000 |  |  |  |  | 50000 |
|  | Exhibition posters with Lamination | Awareness | Starting | 25000 |  |  |  |  |  |  |  |  |  |  |  | 25000 |
| 3 | Printing Broachers-English | Awareness of medical and paramedical personnel | Starting |  | 25000 |  |  |  |  |  |  |  |  |  |  | 25000 |
| 4 | Printing Referral Slips | Referral network documentation | Starting | 6000 |  |  |  |  |  |  |  |  |  |  |  | 6000 |
| 5 | Printing Camp Case paper | Camp registration and documentation | Before first outreach | 5000 |  |  |  |  |  |  |  |  |  |  |  | 5000 |
| 6 | Printing Proforma-fully examined and registered case | Medical Record document | Starting-as general outdoor referred cases screening started | 25000 |  |  |  |  |  |  |  |  |  |  |  | 25000 |
| 7 | Treatment Sheet | Document treatment details | Starting | 2000 |  |  |  |  |  |  |  |  |  |  |  | 2000 |
|  | Meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | General Practitioners-1 | Education and awareness | Starting |  | 5000 |  |  |  |  |  |  |  |  |  |  | 5000 |
| 9 | General Practitioners-2 | Education and awareness | After 3 months |  |  |  |  |  | 5000 |  |  |  |  |  |  | 5000 |
| 10 | General Practitioners-3 | Education and awareness | After 6 months |  |  |  |  |  |  |  |  |  |  | 5000 |  | 5000 |
| 11 | Pharmacist-1 | Education and awareness | Starting |  | 20000 |  |  |  |  |  |  |  |  |  |  | 20000 |
| 12 | Pharmacist-2 | Education and awareness | After 3 months |  |  |  |  |  | 20000 |  |  |  |  |  |  | 20000 |
| 13 | Lab technicians-1 | Education and awareness | Starting | 2000 |  |  |  |  |  |  |  |  |  |  |  | 2000 |
| 14 | Lab technicians-2 | Education and awareness | After 3 months |  |  |  |  | 2000 |  |  |  |  |  |  |  | 2000 |
| 15 | Public | Education and awareness |  | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 3000 | 18000 |
|  | Outreach activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 16 | Outreach Mobile Visit-1 On mobile van with telemedicine connectivity | Diabetic and Diabetic retinopathy screening | Starting month |  | 15000 |  | 15000 |  |  |  |  |  |  |  |  | 30000 |
| 17 | Outreach Mobile Visit-2 On mobile van with telemedicine connectivity at BOU | Diabetic and Diabetic retinopathy screening | Starting month |  |  |  |  | 15000 |  | 15000 |  |  |  |  |  | 30000 |
| 18 | Outreach screening Visit-3 Opportunistic screening | Diabetic and Diabetic retinopathy screening | Starting month |  |  |  |  |  |  |  | 15000 |  | 15000 |  |  | 30000 |
|  | Hospital Activity |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 19 | Screening | To detect +nce and note type of problem | Regularly | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 |  |
| 20 | Investigation-Fundus Fluoresceine Angiography, sonography, Fundus photography | To determine regarding type of treatment. | Regularly | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 | 2500 |  |
| 21 | Laser Treatment | Treatment | Regularly | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 |  |
| 22 | Follow up and investigations | For detection of recurrence and completion of treatment | Regularly | 2000 | 200 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 | 2000 |  |
| 23 | Surgery | To treat complicated cases. | Regularly | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 |  |
| 24 | Salary Project Manager | To report and monitoring of project | Regularly | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 | 10000 |  |
|  | Total Expenditure Rs. Month wise & Grand Total |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1310500 |