Project proposal

To

THE GLOBAL GIVING

2010 OPEN CHALLENG

E-MAIL:	mmehta@globalgiving.org

rsmith@globalgiving.org

From

PAZESA HORTICULTURAL COMMUNITY

Address 			:	penner roberts gardens, Kalichero

C/O Box 511070, chipata

Zambia.

Email 			:	pazesacommunity@yahoo.com.

Project title                :         “ sustainable women,children and youth            empoerment against hiv/aids,poverty and IN-food security .

Location 			:	KALICHERO AGRICULTURAL CAMP,

CHIPATA DISTRICT, Zambia.

Project Duration 	:	12 months (january–december 2011)

CONTACT PERSON 	:	Phiri PAUL: Executive Director

Cell 				:	+260 978 318 517,0964943020.

Email 			:	pazesacommunity@yahoo.com.

Penner Roberts Gardens

P. O. Box 511070

Chipata - Zambia

Cell: +260978318517,+260 964943020

Email: pazesacommunity@yahoo.com

Executive   summary

Project is a rural community initiative technically designed to facilitate viable and sustainable poverty and food – insecurity alleviation and mitigation of the socio-economical impact of HIV / AIDS among households keeping orphans, female headed households, youths and women in Kalichero area through viable and productive utilization of the wetlands (Dambos),HIV/AIDS prevention and impact mitigation.

The main aim of the project is to create and maintain a safe and sustainable, poverty and HIV / AIDS free environment with all year round household owned food security for the vulnerable, disadvantages and under – privileged groups of Kalichero area in Chipata District, Zambia. The project will reach out to 600 households and 2000 individuals as direct beneficiaries through the following activities:-

- Train and empower 200 households keeping orphans affected / infected with HIV / AIDS in viable integrated fish farming.

- Train and empower 200 households keeping orphans and vulnerable children  affected with HIV / AIDS in productive horticultural entrepreneurship for poverty alleviation and food security. .

- Educate 2000 people on the need to stop all forms of violence against children and women through educative sports and theatre

- Educate 1000 people on HIV/AIDS prevention through educative sports, video and theatre shows.

- Expand the organisation income generating activity (fish farming) to ensure sustainability, viability, economic stability and to reduce organisation donor dependance syndrome (DDS) and enhance project continuum.

- Conduct participatory result oriented monitoring and evaluation and facilitate effective running of the managerial duties.

There is need therefore for a grant worth $ 86 375 USD to enable effective implementation of the project for one year. The project has been designed to produce long lasting, viable and sustainable results and impart in beneficiaries a spirit of hard working, determination, innovation and creativity for social economical benefit with special regards to savings for sustainability and economic stability. PAZESA Horticultural Community has dedicated an account bearing the following particulars to the project:

Account Name 		: 	PAZESA Horticultural Community

Account Number 	: 	0084693305001

Bank Name 		: 	Finance Bank Zambia Ltd.

Branch Name 		:	Chipata Branch

Branch Code 		:	008

Swift Code 		:	ZFBAZMLU

Bank Address 		:	fbchipata@financebank.co.zm.

PAZESA has competent and experienced personnel to professionally execute a project of his scope and magnitude. The organisation has been in partnership with firelight foundation of California in the USA. For reference please email the Director of programs; Zanele Sibanda Knight on; Zanele@firelightfoundation.org. or the district aquaculturist at Chipata Aquacultural station on edgarkabeke@yahoo.uk.co

It is our utmost anticipation that our request shall be favorably considered.

We thank you for your most considerate regard of the rural underprivileged people in advance.

Yours Faithfully,

Phiri   Paul

EXECUTIVE DIRECTOR.

Penner Roberts Gardens

P. O. Box 511070

Chipata - Zambia

Cell: +260978318517,+260964943020

Email: pazesacommunity@yahoo.com

20 th august, 2010

The Executive Director,

GLOBAL GIVING-OPeN CHALLENGE

donors and well wishers

Dear / Madam,

RE:	financial support to help facilitate “SUSTAINABLE WOMEN,CHILDREN AND YOUTH  EMPOWERMENT AGAINST HIV/AIDS,POVERTY AND FOOD INSECURITY Project.

The writing hereunder expresses the need for your most charitable organisation the world over to support PAZESA Horticultural Community implement a “women, children and youth empowerment against HIV/AIDS, POVERTY AND FOOD-INSECURITY project in Kalichero Agricultural Camp of Chiparamba block in Chipata District of Zambia.

PAZESA Horticultural Community is a rural community based non governmental, non profit, humanitarian organization duly registered with the Registrar of Societies in Zambia under certificate number ORS / 102/16/715 and base in Kalichero area at Penner Robert Gardens.

The  Project has been technically designed to deliver viable and sustainable result oriented initiatives for best and most productive wetland utilization reaching out to 600 household and 2000 individuals respectively as direct beneficiaries through the following activities:-

- Train and empower 200 households keeping orphans affected / infected with HIV / AIDS in viable integrate fish farming.

- Train and empower 200 households affected with HIV / AIDS in productive horticulture for food security through irrigation farming and entrepreneurship for poverty alleviation .

- Train and empower 300 people on the need to stop all forms of violence against children and women both at household and community level.

- Conduct HIV/AIDS PREVENTION campaign through trainings, educative theatre, educative video shows and educative sports

- Provide blankets and shoes to 200 orphans and vulnerable children

- Educate 2000 people on the best and most productive utilization of the neglected wetlands through knowledge exchange visits and field exhibitions.

- Expand the organisation income generating activity (fish farming) to ensure sustainability, viability, economic stability and to reduce organisation donor dependance syndrome (DDS) and enhance project continuum.

- Conduct participatory result oriented monitoring and evaluation and facilitate effective running of the managerial duties.

There is need therefore for a grant worth $ 86 375 USD (ZK345 200 000.00)   to enable effective implementation of the project for a period of one year.

PAZESA Horticultural Community has competent staff to professionally execute a project of this scope and magnitude. The organisation is in partnership with firelight foundation of USA and Chipata Aquacultural Station. For reference please email the Director of programs at  firelight foundation on: Zanele@firelightfoundation.org and the provincial fish culturist in Chipata on: edgarkabeke@yahoo.co.uk

Your keen consideration for the rural under privileged poor is highly appreciated in advance.

Yours Faithfully,

Phiri   Paul.

Executive Director.

PROJECT PROPOSAL OUTLINE

    - PROJECT TITLE 	:“Women, Children and Youth Empowerment against HIV/AIDS,    POVERTY AND FOOD-INSECURITY project .

2.0.0.	APPLICANT 		:	PAZESA Horticultural Community.

3.0.0.	OPERATION AREA 	:	Kalichero Agricultural camp, Chiparamba block,

Chipata District, Zambia covering 8 zones.

4.0.0.	DURATION 		:	One year, January 2011 to December 2011.

  - PREAMBLE

Being presented hereunder is the need for your most charitable organisation to help PAZESA with financial, technical and / or material support to enable effective implementation of the “Women, Children and Youth Empowerment against HIV/AIDS,    POVERTY AND FOOD-INSECURITY project The project is a truly viable rural community initiative and sure strategical intervention through which to alleviate high levels of poverty, food- insecurity, unemployment, malnutrition and underdevelopment so as to mitigate the socio-economical impact of HIV/AIDS in the area.

  - PROBLEM STATEMENT ANALYSIS /RATIONALE.

Kalichero area in Chiparamba is approximately 27km Northwest of Chipata town along Mfuwe road.  The area is highly accessible and has a growing population of over 30 000 people.  98% of all inhabitants are subsistent farmers absolutely dependant on the erratic rainfall pattern 80% of the total population are below 49 years old.  The area harbors absolute poverty such that the average households eat once the other day especially between October and March of each calendar year and lives on less than $1 US dollars per day, per household.  High poverty levels constrain procurement of both Agricultural inputs and implements and as a result prolonged low Agricultural productivity dominates the area.  Consequently, low agricultural productivity causes (is responsible for) severe food insecurity which facilitates hunger and malnutrition.  Furthermore, the erratic rains experienced consecutively further deepen the inhabitant’s vulnerability to poverty.  This awesome situation forces most female youths and widows to use their sexual skill (prostitution) to acquire either food, money or both in order to survive.

Regrettably, under such pressing high risk situation the women have neither the skill nor the capacity to negotiate for safer and protected sex.  As a result there are high levels of HIV/AIDS, teenage pregnancies, premarital pregnancies, extra-marital sexual affairs and sexually transmitted infections.  (Source: National gender policy 2005).

Most outstanding however is that PAZESA Horticultural community in conjunction with the community has designed a project to facilitate sustainable economical development and mitigation of the socio-economical impact of HIV/AIDS in Kalichero through viable and productive utilization of the wetlands to address issues of :High HIV/AIDS prevalence in a high poverty stricken rural area with very low agricultural productivity causing severe food insecurity which perpetrates high risk sexual behaviour especially among youths, women, orphans and vulnerable children and female headed households.

  - PROJECT JUSTIFICATION AND IMPLEMENTATION METHODOLOGY.

The project is a sure intervention through which to alleviate poverty, food insecurity, unemployment and curb further HIV/AIDS spread.  The project trains beneficiaries how best to utilize the available wetlands for maximum economic benefit in an environmentally friendly, ecologically symbiotic way.  The fish farming integrates with Agro-forestry, horticulture and cereal production.  Thus each sector uses raw materials from another sector and vice versa.  Fish farming is pure organic farming.

The products will enable the beneficiaries to be self sustainable such that people living with HIV/AIDS will no longer depend on baby fish (kapenta) rations from home based care centres.  All trainings and empowerment shall be guided by the “save yourself account” policy i.e. whatever income beneficiaries earn must account for 20% savings either using village Banking or Western Banking methodologies.  Beneficiaries shall also be encouraged to empower one more household (revolving fund strategy).  The intervention in this project are capable of replicating and even triplicate productivity, income generation and food security thus improving the socio-economic standard of the marginalized people of Kalichero in Chiparamba.

  - VISION

To create and maintain a safe and sustainable, poverty and HIV/AIDS free living environment with all year round household owned food security for the vulnerable, marginalized and disadvantaged inhabitants of Kalichero area in Chiparamba Chipata, Zambia, through practical and viable exploration of the available wetlands for sustainable strategies and initiatives that reinforce result oriented cost effective socio-economic benefit to the rural community by 2013.

  - SPECIFIC PROJECT OBJECTIVES

  - To reduce high levels of poverty among 200 households keeping orphans affected / infected with HIV/AIDS through viable and sustainable integrated fish farming in Kalichero by December . 2011.

  - To facilitate all year round household owned food security and improved income among 200 households in Kalichero through facilitation of viable horticulture entrepreneurship and irrigation farming by December 2011.

  - To educate 300 people on the need to stop all forms of violence against children and women in chiparamba area by December, 2011.

  - To educate 1000 people especially the youths on the best HIV/AIDS prevention strategies though educative sports, theatre and video shows.

  - To mitigate the socio-economical impact of HIVAIDS and poverty to 200 orphans and vulnerable children in Kalichero area by December 2011through provision of blankets and shoes.

  - To educate 2000 people on the best and most productive, viable and sustainable wetlands utilization to alleviate poverty, food insecurity, low productivity and the socio-economic impact of HIV/AIDS by December 2011.

  - To expand the basis for project / organisation economic stability and reduce the organisation Donor Dependancy Syndrome (DDS) so as to allow project continuum and ensure sustainability reliability and viable economic stability by December, 2011.

  - To keep track of the project activities and facilitate effective running of the managerial duties through out the project cycle.

  - ACTIVITIES TO BE UNDERTAKEN WITH THE FUNDS

  - Train and empower 200 households keeping orphans with the productive means for viable and sustainable integrated aquaculture (fish farming)

  - Train and empower 200 households in viable horticulture entrepreneurship and food security through irrigation.

  - Train and empower 300 people to stop all forms of violence against children and women .

  - Educate 1000 individuals on the best HIV/AIDS prevention strategies .

  - Provide blankets and shoes to 200  OVCs

  - Conduct knowledge exchange learning visits and exhibitions.

  - Establish 10 x 1200m² fish ponds and a processing / market centre for project continuum and organisation sustainability.

  - Conduct participatory monitoring and evaluation of the project and facilitate effective implementation of the managerial duties

  - IMPORTANCE OF THE PROJECT IN RELATION TO THE OBJECTIVES

The SWCE project is highly important since the project is native born, proven, innovative and most importantly, offers the best utilization of the ever neglected wetlands (dambos).  It empowers the rural community to be productive ACTORS and not perpetual BEGGARS for food relief.  It trains and empowers beneficiaries with proven productive means with which to raise food, income, reduce poverty and unemployment and curb HIV/AIDS in the area.  Confidently, raising both food security and income will offset the sex for money and / or food trend.  People living with HIV/AIDS (PLWHA), orphans and vulnerable children, women and youths will be among the prime target beneficiaries classified as the most vulnerable, disadvantaged high risk but determined groups.

PAZESA Horticultural community in partnership with firelight foundation has been undertaking similar activities for more than 3 years and hence the organisation has exception experience of the activities. For reference please contact the Director of programmes for firelight foundation on: zanele@firelightfoundation.org or the provincial fish culturist at Chipata Government fish farm on: edgarkabeke@yahoo.co.uk

  - EXPECTED IMMEDIATE RESULT (OUT PUTS)

  - 200 households trained and empowered with viable and sustainable fish farming techniques.

  - 200 households trained and empowered to undertake viable horticulture entrepreneurship to alleviate poverty and food insecurity.

  - 3000 people  trained and empowered to facilitate measures to stop violence against children and women

  - 1000 people empowered with strategies to prevent further HIV/AIDS spread.

  - 200 OVCs empowered with blankets and shoes

  - 2000 individuals educated on the best and most productive utilization of wetlands to alleviate poverty, low productivity, food insecurity and reduce the socio-economical impact of HIV/AIDS.

  - 10 x 1200m² fish ponds and a 1 fish processing / packing centre established for enhanced project sustainability, continuum, viability and solidarity.

  - 1 project video documentary manifesting project achievements starting with beneficiary’s baseline state, vision, and services delivered, achievements, challenges, constraints, accountability, transparency, quality performance and project sustainability and impact in honour the donor.

- A total of 400 households and 5200 individuals as direct beneficiaries.

  - EXPECTED PROJECT OUTCOME

  - At least 1200 individuals from 200 households live sustainable with improved income and reduced poverty all year round due to viable fish farming empowerment.

  - Atleast 1200 individuals from 200 households live sustainable with reduced poverty all year round due to viable horticulture entrepreneurship.

  - At least 1200 individuals from 200 household live sustainable with food security all year round due to maize production through irrigation.

  - A community empowered with viable and sustainable livelihood activities through best utilization of wetlands.

  - Reduced poverty, low productivity food –insecurity and vulnerability to HIV/AIDS for the vulnerable and high risk groups of the community.

  - Monitoring and evaluation logframe.

| Activity | Expected out put / target | Out put indicator (Indicate type) | Means of verification |
| --- | --- | --- | --- |
| Train and empower 200 household in fish farming. | 200 households to be trained and empowered. 8 trainings to be conducted | # of household trained. # of trainings conducted. | Activity Participant register Financial reports |
| Train and empower 200 household in Horticulture | 200 households to be trained and empowered. 5 trainings to be conducted. | # of household trained. # of trainings conducted. # of pumps procured | Activity Participant register Financial reports |
| Train and empower 3000 individuals in HIV/AIDS prevention through sports. | 3000 individuals to be trained and empowered. | # of individuals trained. # of ports competition conducted. | Activity Participant register Financial reports |
| Educate 2000 individuals on best / productive wetland utilization. | 2 knowledge exchange to be conducted | # of people trained. # of exhibitions conducted. # of visits conducted. | Activity Participant register Financial reports |
| 1000 people to be trained in children’s ’/women’s rights | 4 campaigns to be conducted 2trainongs to be conducted | # of people trained # of people reached. | Activity report Financial report Participant register |
| 200 orphans and vulnerable children to be given blanket/shoes | 200 orphans to be empowered. | # of orphans and vulnerable children empowered | Participant register Financial report Activity report. |
| Expand organization fish farming | 10 fish ponds to be established. 1 processing centre to be established. 72 000 fingerlings to be procured and stocked. 10 fish ponds to be stocked. | # of fish ponds established. # of processing centers established. # of fingerlings procured. | Activity Participant register Financial reports Progress report |
| Monitoring and Evaluation. | 1 video documentary to be procured. All project targets to be captured. 3 motor bikes to be procured. | # of video documentaries produced. % of target achieved. # of motorbikes procured. | Monthly, quarterly, annual report. Monitoring and Evaluation reports Financial reports. |

Note: 		# Denotes Number.

15.0.0.    ACTIVITY WORK PLAN.

| # | Activity | Responsible person | Time line (in months) August 2010 – july, 2011. |
| --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |
| 1 | Train / empower 200 households in fish farming | Monitoring Officer, program Officer |  |  |  |  |  |  |  |  |  |  |  |  |
| 2 | Train / empower 200 household in horticulture | Monitoring Officer, program Officer |  |  |  |  |  |  |  |  |  |  |  |  |
| 3 | Train / empower 200 H/H in maize production. | Program Officer |  |  |  |  |  |  |  |  |  |  |  |  |
| 4 | Educate 2000 individuals | Monitoring Officer, Program Officer |  |  |  |  |  |  |  |  |  |  |  |  |
| 5 | Expand organisation fish farming | Finance Officer, Director |  |  |  |  |  |  |  |  |  |  |  |  |
| 6 | Monitoring and Evaluation | Monitoring Officer, Director. |  |  |  |  |  |  |  |  |  |  |  |  |
| 7 | Administration | Director, Finance / Admin’ Officer. |  |  |  |  |  |  |  |  |  |  |  |  |
| 8 | Internal reporting | All project staff |  |  |  |  |  |  |  |  |  |  |  |  |
| 9 | External reporting to donors * | Finance Officer M & E Officer, Director. |  |  |  |  |  |  |  |  |  |  |  |  |

Note: 		* Subject to change depending on donor conditions.

16.0.0. SUSTAINABILITY, replicability and documentation.

The Project has been technically designed to deliver long lasting viable livelihood skills / activities incorporated in the project. Effective activity implementation is reinforced by the presence of the implementing agent right in the midst of the beneficiaries to enhance ownership and coax adoption. The irrigation equipments to be distributed are manual powered triddle pumps to ensure minimal cost of running and maintenance and ensure sustainability. The organisation income generating activity (fish farming) shall ensure project continuum after donor fund phases out. The project staff shall provide free consultancy to potential project replicators.

Furthermore, all success stories and project achievements shall be properly documented and broadcasted through a Global Giving proven media and specific documentaries submitted to the Global Giving to manifest and honour the most considerate and outstanding donor.

17.0.0. Monitoring and evaluation.

Participatory result oriented monitoring and evaluation methodology shall be used to ensure complete community participation at all stages of the project. Both qualitative and quantitative data and parameters shall be obtained. Data collection tools such as training registers, empowerment registers, food security tracking forms, activity reports and financial reports shall be used to collect data during implementation. Such tools as monitoring and evaluation matrices, questionnaires, stake holders meetings, on sport checks, impact assessment survey and project video documenting shall be used to manifest and ensure transparency, relevance, accountability, reality and quality performance.

18.0.0. BRanding and marking

All valuable products and equipment procured using Global GIVING funds shall be marked with the specific donor’s graphic identity (logo) and PAZESA Horticultural Community Logo in a way most preferred by the Global GIVING. A large billboard (post) shall be established in the project site to honor the donor.

19.0.0. Organisation administration structure.

PAZESA horticultural Community comprises the Executive committee, the Community Advisory board and works by forming Community Action groups. The activities are implemented by the Executive committee and volunteers; peer educators, caregivers and mentors.

19.1.0. The executive committee consists of 5 members as follows:-

19.1.1. The executive Director, Mr. Paul Phiri, 36 years old, who has certificates in

Project management, monitoring and evaluation, financial management, participatory learning and Action, HIV/AIDS impact mitigation (BIZAIDS) Horticulture and certificate in USAID and PEPPAR Grants and financial management and is computer literate plus 13 years experience in community development.

19.1.2. 	The monitoring and evaluation Officer Mr. Banda Milson , 45 years of age and has     certificates in general agriculture, HIV / AIDS impact mitigation and certificate in monitoring and evaluation and 20 years work experience in rural community development.

19.1.3. The finance and Administration Officer, Ms Setridah Banda, 40 years of

age, who has certificate in accounts, certificate in financial and accounting management systems (FAMS) with ZICAS and Currently studying Diploma in accounts. Certificate in Secretarial and data entry with 8 years experience in community development.

19.1.4. The program officer, Mr. Simenda Simenda, 34 years old, who has

Certificate in Basic computer application, certificate in Disaster management and HIV / AIDS impact mitigation plus 5 years experience in community development.

19.1.5. The program officer, Ms Tembo Sharon, 28years old, who has certificate in

HIV / AIDS information dissemination, computer services social work and 5 years experience in community development.

20.0.0. Organisation bank information and financial management system.

PAZESA horticultural Community has dedicated to the SWCE project a Bank Account bearing the following details.

Account Name 		: 	PAZESA Horticultural Community

Account Number 	: 	0084693305001

Bank Name 		: 	Finance Bank Zambia Ltd

Branch Name 		:	Chipata Branch

Branch Code 		:	008

Swift Code 		:	ZFBAZMLU

Bank Address 		:	fbchipata@financebank.co.zm.

The organisation is committed to maintaining high levels of accountability and transparency and as such the account is managed by four (4) Signatories in two different panels. Payment authorization is effective is signed by atleast two signatories, one from either panel including the principal signatory.

Necessary financial control mechanism and tools for both protect and detect controls are used. Tools such as cash requisition, payment voucher, cheque register, activity financial reports, (receipts), asset registers, monthly financial reports, cash book, etc are used to ensure transparency and accountability.

Penner Roberts Gardens

P. O. Box 511070

Chipata - Zambia

Cell: +260978318517

Email: pazesacommunity@yahoo.com

PROPOSED BUDGET BREAKING TO ACTIVITY LINE  EXCHANGE RATE

:($ USD = ZMK 4000)

| # | Activity / Item | Qty | Frequency | Unit Cost ZK | Total Cost |
| --- | --- | --- | --- | --- | --- |
|  |  |  |  |  | ZMK | USD $ |
| 1 | Train and empower 200 households in aquaculture Resource Fees Resources materials Food Conference facility Fingerlings Packaging materials Transport for fingerlings | 2 50 50 1 500 50 1 | 4x2days 4 4x2days 4x2days 50 4 4 | 100,000 10,000 10,000 200,000 500 10,000 300,000 | 1,600,000 2,000,000 4,000,000 1,600,000 12,500,000 2,000,000 1,200,000 | 400 500 1000 400 3125 500 300 |
|  | SUB-TOTAL |  |  |  | 24,900,000 | 6,225 |
| 2 | Train and empower 200 households in food security Resource fees Resource materials Food Conference facility Inputs Pressure pumps Transport for pumps / inputs | 2 50 50 1 50 2 1 | 4 x 2days 4 4 x 2 days 4 x 2 days 4 4 5 | 100,000 5,000 10,000 100,000 50,000 1,300,000 300,000 | 1,600,000 1,000,000 4,000,000 800,000 10,000,000 10,400,000 1,500,000 | 400 250 1000 200 2500 2600 375 |
|  | SUB – TOTAL |  |  |  | 29,300,000 | 7,325 |
| 3 | Stop violence against children / women Resource Fees Resources materials Food Conference facilities Educative theatre Educative sport | 2 25 25 1 4 2 | 2days 2 2x2days 2x2days 12months 12months | 100,000 10,000 10,000 100,000 200,000 500,000 | 400,000 500,000 1,000,000 400,000 9,600,000 12,000,000 | 100 125 250 100 200 500 |
|  | SUB - TOTAL |  |  |  | 23,000,000 | 5750 |
| 4 | Conduct HIV/AIDS Prevention campaign Peer Educators Training Educative video shows Educative theatre shows Educative sports Stationery | 1 4 4 2 1 | 1 12 6 12 12 | 8,400,000 300,000 200,000 500,000 300,000 | 8,400,000 14,400,000 4,800,000 12,000,000 3,600,000 | 2,100 3,600 1,200 3,000 9,000 |
|  | SUB – TOTAL |  |  |  | 43,200,000 | 10,800 |
| 5 | Provision of Blankets and shoes Blankets Shoes Transport | 50 50pairs 1 | 4 4 4 | 50,000 50,000 300,000 | 10,000,000 10,000,000 1,200,000 | 2,500 2,500 300 |
|  | SUB – TOTAL |  |  |  | 21,200,000 | 5,300 |
| 6 | Knowledge exchange visit / exhibitions Transport Food for exchange visits Food for exhibition | 1 500 450 | 4 4x2 meals 4 | 2,000,000 10,000 10,000 | 2,000,000 4,000,000 18,000,000 | 500 1,000 4,000 |
|  | SUB – TOTAL |  |  |  | 24,000,000 | 6,000 |
| 7 | Expand fish farming (sustainability) Fish ponds establishment Fingerlings Feed (bags) Processing / Packaging centre Fridge Cooler box Solar module Packaging materials Heat sealer | 1 5000 50 1 1 10 2 1 1 | 10 10 6 1 1 1 1 4 1 | 500,000 500 20,000 3,000,000 2,400,000 250,000 3,500,000 300,000 300,000 | 5,000,000 25,000,000 6,000,000 3,000,000 2,400,000 2,500,000 7,000,000 1,200,000 300,000 | 1,250 6,250 1,500 750 600 625 1,750 300 75 |
|  | SUB – TOTAL |  |  |  | 52,400,000 | 13,100 |
| 8 | Monitoring and Evaluation Stationery Motor bikes Documentary Quarterly evaluation meetings Fuel | 1 3 1 1 1 | 12 1 4 4 12 | 200,000 6,000,000 1,000,000 1,200,000 500,000 | 2,400,000 18,000,000 4,000,000 4,800,000 6,000,000 | 600 4,500 1,000 1,200 1,500 |
|  | SUB – TOTAL |  |  |  | 35,200,000 | 8,800 |
| 9 | Administration Stationery Communication (wireless internet) Transport Office supplies Computer Printer Staff upkeep allowances- Director M&E Officer Finance Officer Program Officer Secretary | 1 1 1 1 2 1 1 1 1 2 1 | 12 months 12 months 12 months 12 months 1month 1 month 12 months 12 months 12 months 12 months 12 months | 300,000 300,000 500,000 100,000 6,000,000 3,500,000 1,500,000 1,000,000 1,000,000 600,000 500,000 | 3,600,000 3,600,000 6,000,000 1,200,000 12,000,000 3,500,000 18,000,000 12,000,000 12,000,000 14,400,000 6,000,000 | 900 900 1,500 300 3,000 875 4,500 3,000 3,000 3,600 1,500 |
|  | SUB – TOTAL |  |  |  | 92,300,000 | 23,075 |
|  | TOTAL PROJECT COST |  |  |  | 345,500,000 | 86,375 |

# Text boxes

PAZESA COMMUNITY

PAZESA COMMUNITY

PAZESA COMMUNITY

PAZESA COMMUNITY

PAZESA COMMUNITY