Climate Change Awareness to Farmers and Plantation

Vision

This project is to create awareness on climate change among 250 marginalized farmers, plantation of seedling in afforest region in target area, and strengthen the organic farming.

Needs of the Project

United Nations Organization Says about Climate change is considered to be a critical global challenge and recent events have demonstrated the world’s growing vulnerability to climate change. The impacts of climate change range from affecting agriculture to further endangering food security, to rising sea-levels and the accelerated erosion of coastal zones, increasing intensity of natural disasters, species extinction and the spread of vector-borne diseases. Many trees were cut down for domestic purposes in the target area. So the target region is going to afforest region. Many farmers are not aware of climate change and organic farms in this area.

Hence the project is to create awareness on Climate Change among farmers and to reduce Carbon-di-Oxide which is also one of the reasons for Climate Change. Carbon-di-Oxide can be reduced by plantation of seedling in afforest region in Madurai North Block Rural Areas. This project is also strengthening the organic farming.

Awareness activities

  - Two Days Workshop on Agricultural and Climate Change for Farmers

  - Poster/banner advertisement for Climate Change in target area

  - Preparation and use/distribution of resource materials for Farmers

  - Preparation and demonstration of Vermicompositing for Farmers which is strengthening organic farming

  - Distribution of seedling of local and forest plant species for Farmers

Action components

- Establishment of a Nursery to Grow Local and Forest Plant Species

- Plantation of seedling of local and forest plant species in and around target village afforest region.

Theme (s)

Ecosystem and Biodiversity conservation

Target groups

250 Marginalized Farmers are from Madurai North Block villages.

Locations

Madurai North Block Rural Areas

Dates and durations

Awareness Activities Date: 15-03-2011

Action Component: From 15-12-2010 to 14-03-2011

JUSTIFICATION

- Describe, Demonstrate and encourage the coexistence of crops and other trees, organic farming, water and soil conservation, preparation of Vermicompositing and such other eco-friendly techniques.

- To establish a good nursery that grows a substantial number of local and forest plant species.

- Use these to afforest regions in and around the target villages, and distribute seedlings to farmers at free of cost.

- Encourage farmers to grow trees by describing the economic advantages to the owner in addition to the beneficial effects it has on their land and the ecosystem itself.

Success indicators

250 farmers would get awareness over the biodiversity conservation, and 250 farmers would take up of preparation training of Vermicompositing.

Plan of implementation

First we propose to establish a nursery garden to grow local and forest plant species for three months and then to conduct Two days workshop, and distribution of seedlings to for Farmers and plantation of seedlings in and around the target areas

Follow up

Our Staff Member monitoring the Programme at weekly once and they give weekly report to the office and monthly report to the Trust Managing Committee during and after the project period

BUDGET

Awareness component

Budget for awareness component

| S.No. | Component | Amount in US $ |
| --- | --- | --- |
|  | Rent for Hall to conduct three work shops | 600 |
|  | Raw Materials for demonstration of Vermicompositing etc… | 500 |
|  | Printing and distribution charges for Resource Materials , Charts, Wall post, Banner, etc. | 1250 |
|  | Honorarium for Resource Persons | 500 |
|  | Audio and video arrangements | 450 |
|  | Total | 3300 |

Action component

Budget for action component

| S.No. | Component | Amount in US $ |
| --- | --- | --- |
| 1 | Raw Materials and Seeds for forming Nursery Garden | 5000 |
| 2 | Maintenance work of Nursery Garden for three months | 750 |
| 3 | Plantation of seedling in and around Target village afforest regions | 5500 |
|  | Travel Expenses | 750 |
| 4 | Follow up work | 3000 |
|  | Total | 15000 |

| S.No. | Component | Amount in US $ |
| --- | --- | --- |
| 1 | Awareness component | 3300 |
| 2 | Action component | 15000 |
|  | Total | 18300 |

Conclusion

Grace Peter Charitable Trust would implement the project to its level best. It will bring out significant changes and valuable results through this project for the development of the target area. So we request the donors to consider this project positively. We hope that we would be given an opportunity to work for the said target group and target area.