Project Proposal

On:

Improving nutrition among Children under 5 years

(CU5) and Women of Reproductive age (WORA)

By:

Together Ghana Organisation

Part 1 Title Page

| Proposal Title: | FEED THE BODY PROJECT(FTBP) |
| --- | --- |
| Organization: | TOGETHER GHANA (NGO) |
| Contact Address: | Noah Dumahasi TOGETHER GHANA P.O.BOX 159,HOHOE,VOLTA REGION ,GHANA Phone: +233(0)935 20197 Email: togetherghana@yahoo.co.uk |
| Region(s) and Population(s) targeted: | VOLTA REGION 5,000 Children under 5 and Women of Reproductive age from 20 villages in the Nkwanta South District in Ghana. |
| Proposed Duration: | Ongoing |
| Total Project Cost | 21,850 Dollars |
| Bank Information: | ACC. NAME:- TOGETHER Ghana ACC. NO.:- 5111010091285 BANK SWIFT: GHCBHAC BANK ADDRESS: HOHOE. |

PART II Project Description

2.1 Rationale of the Project

Nutrition plays an important role in the health and welfare of children and women in Ghana. Adequate food and sound nutrition are essential to good health. They are crucial for human survival, for prevention of and recovery from illness. Economic evidence also suggests that life expectancy is directly related to poverty and nutrition. Malnutrition (Poor nutrition) results in morbidity, mortality, poor education and fewer opportunities for economic development. Poor education, low socio-economic status and high fertility are factors that may influence the nutritional status of an individual. In Ghana, children under five years and women of reproductive age are the most vulnerable to poor nutrition-Ghana Demographic and Health Survey (GDHS) 2003 Nutrition page 169. Iron-deficiency anemia is a major threat to maternal health,65% of pregnant women, 59% of lactating mothers, 71% of school-age children and 84% of preschool children were found to be anemic according to the baseline on study on prevalence and etiology of anemia conducted in 1995 (GHS,1995). Out of the 1210 people who reported anemia case in Nkwata Hospital in the project area as per 2008 monthly out-patients morbidity returns, 32% are under 5years and 25% are women of childbearing age. The challenge is to reduce morbidity and mortality due to anemia and other micronutrient deficiencies in Ghana (GDHS) 2003 Nutrition page 182. PROBLEM TREE:CAUSE- EFFECT RELATIONSHIP OF “FEED THE BODY PROJECT” Poor Education High mortality and morbidity Low Economic development EFFECTS Poor nutrition among Children under 5 years (CU5) and Women of reproductive age (WORA) CORE PROBLEM Low complementary food intake for Infants above 6 months Short Exclusive Breastfeed for infants under 6 months Low micronutrients Intake among CU5 and Women CAUSES Inaccessibility of nutritious variety of foods to rural areas Poor quality foods Inadequate supply of Vitamins, iron and zinc

2.2 Objectives of the Project

OBJECTIVE TREE: MEANS – ENDS RELATIONSHIP OF “FEED THE BODY PROJECT” Increased Economic development High Education Low mortality and morbidity rate Improved nutrition among Children under 5 years (CU5) and Women of Reproductive age (WORA) CORE OBJECTIVE High complementary food intake for Infants above 6 months Reduced nutritional anemia among CU5 and WORA Increase micronutrients Intake among CU5 and Women Nutritious variety of food accessible to rural communities Improved food quality Adequate supply of Vitamins, iron and zinc Specific Objectives: 1. Increased intake of micronutrients for 1000 Children under five years and 1000 Women of Reproductive Age(WORA) residing in 20 rural communities without health facilities in Hohoe municipal area of Volta Region in Ghana by the end of 12 months. 2. Reduced nutrition anemia among 1000 children under five years and 1000 women of reproductive age residing in 20 rural communities without health facilities in Hohoe municipal area of Volta Region in Ghana by the end of 12 months.

2.3 Expected Outcomes of the Project

Increased knowledge of nutrition literacy skills. Increased intake of nutritious complementary food for infants above 6 months. Reduced micro nutrient deficiencies among Children under five years (CU5) and women of reproductive age (WORA).Reduced nutritional anemia among CU5 and WORA OUTCOMES; Objectively Verifiable Indicators (OVI); Monitoring Mechanisms; EXTERNAL FACTORS. 1.Increased knowledge of nutrition literacy skills 2.Increased intake of nutritious complementary food for 1000 infants above 6 months by 60% over the baseline within 12 months; Community-level Nutrition Literacy Campaigns in months 1-3. Nutrition Information Education Communication(NIEC) materials adapted and distributed in months 2-3. Women with CU5 trained. Energy density micronutrient-rich complementary food supplied in months 2-10.; Community sensitization report Copies of NIEC materials adapted and distributed Training report Distribution list of Complementary Food Project Implementation progress report; Community level support Continued cooperation from Hohoe Municipal Health Directorate Full participation of target group Childbearing Women access the facility. 3.Reduced micronutrient deficiencies among 1000 CU5 and 1000 WORA by 50% over the baseline within 12 months; Vitamin A and B supplementation 2 times in 12 months; Distribution List of Vitamins /Dietary supplementation Project Implementation progress report; Dispatch of Vitamins/Minerals on a timely basis from SIGHT and LIFE No encumbrances at point of Delivery Childbearing Women access the facility. 4.Reduced nutritional anemia among 1000 CU5 and 1000 WORA by 50% over the baseline within 12 months; Minerals-Iron and Zinc Supplementation in months 3-11; Distribution List of Minerals/Dietary supplementation Project Implementation progress report.

2.4 Detailed Approach Plan of the Project

Project Summary; OVI; Monitoring Mechanisms; External factors. OBJECTIVES: 1. Increased intake of micronutrients for 1000 CU5 and 1000 WORA. 2. Reduced nutrition anemia among 1000 CU5 and 1000 WORA.; 1000 CU5 and 1000 WORA residing in 20 rural communities without health facilities intake of micronutrients increased by 60% over the baseline by the end of 12months. Nutritional anemia among 1000 CU5 and 1000 WORA residing in 20 rural communities without health facilities reduced by 50% by the end of 12months.; Project Progress Implementation reports; Continued cooperation with Municipal Directorate of Health Services Continuous community level support. OUTCOMES: 1. Improved nutrition literacy knowledge. 2. Increased intake of nutritious complementary food for 1000 infants above 6 months. 3. Reduced micronutrient deficiencies among 1000 CU5 and 1000 WORA. 4. Reduced nutritional anemia among 1000 CU5 and 1000 WORA.; Community-level Nutrition Literacy Campaigns in months 1-3.launched Nutrition Information Education Communication(NIEC) Materials adapted and distributed in months 2-3. Women with CU5 Trained on nutrition skills Energy density micronutrient-rich complementary food supplied in months 2-10. Vitamin A and B supplementation 2 times in 12 months Minerals-Iron and Zinc Supplementation in months 3-12; Community sensitization report Community Nutrition Literacy Classes held and reported Copies of NIEC materials adapted and distributed Training report LPOs, Invoices and Receipts of Purchases. Distribution list of Complementary Food Distribution List of Vitamins /Dietary supplementation Distribution List of Minerals/Dietary supplementation Project Implementation progress reports; Continuous community level support Full participation of target group Market prices remain Stable Target group access the facility. ACTIVITIES: 1. Organize Community sensitization on Nutritional literacy 2. Form groups of women with children under five. 3. Develop/Adapt NIEC materials for dissemination. 3. Train groups on Nutrition literacy skills 4. Purchase energy density micronutrient-rich complementary food for distribution to CU5. 5. Delivery of Vitamins and Minerals 6. Distribute Vitamin and Minerals to CU5 and pregnant women; 20 Communities sensitized on Nutritional literacy 40 Groups of WORA with CU5 ,each with 25 members, formed 1100 copies of NIEC materials disseminated 40 Groups trained on Nutritional literacy skills in single group settings. 2 rations of Complementary food distributed to 1000 CU5 Vitamins and Minerals received and documented Vitamins and Minerals distributed 2 times of 6 month interval; List of communities sensitized Comprehensive List of community, groups and members Copies of NIEC and its distribution list. Training reports LPO, Invoices and receipts Comprehensive list of items, community and recipients Goods issued notes and Distribution list; Community support Training is appropriate, effective and practiced Market prices are stable Counterpart budget is available on a timely basis. INPUTS: - Consultant - Community mobilization - Complementary food - Training /IEC materials - Distribution; $ Consultant 1,000 Community Mobilization 1,500 Complementary food 10,000 Training/ IEC Materials 2,500 Distribution 1,500 $16,500; Project Implementation Progress reports Project Accounts; Consultants are competent. Communities are cooperative..

2.5 Process and Outcome Evaluation Plans of the Project

ACTIVITIES; OUTCOMES; MEANS OF VERIFICATION. WHO; HOW; WHEN; FREQ.; DATA. 1. Organize Community sensitization on Nutritional literacy; 1.Increased knowledge on Nutrition Literacy Skills; Project Team (PT); Community durbar; Month 1; Once in each of the 20 communities; Sensitiz’n report. 2. Form groups of women with children under five. (WWCU5); PT; Community selection of WWCU5.; Month 2; Once in each of the 20 communities; List of WWCU5. 3. Develop/Adapt NIEC materials for dissemination.; PT + Consul- tant; Adapt , Translate & Print NIEC materials; Month 2-3; Once of 1100 copies; Copies available. 3. Train groups on Nutrition literacy skills; PT + Consul- tant; In Single Group setting; Month 3; One day for 2 groups in each of 20 communities; Training report. 4. Purchase energy density micronutrient-rich complementary food for distribution to CU5.; 2. Increased intake of nutritious complementary food for 1000 infants above 6 months.; PT + Consul- tant; Suppliers purchase; Month 4; 3 different supplies; LPO, Invoices Receipts Distrib’n Returns Field Data Collect’n Forms (FDCF). 5. Take delivery of Vitamins and Minerals from SIGHT AND LIFE.; 3. Reduced micronutrient deficiencies among 1000 CU5 and 1000 WORA.; PT + Consul- tant; Clearing Documents (CD); Month 1; Once; CD Goods Received Notes (GRN). 6. Distribute Vitamin Supplements to CU5 and pregnant women; PT + Consul- tant; Gather and Analyse Field and Hospital data; Month 2-8; Quarterly; FDCF Monthly Out-Patients Mortality Returns (MPMR). 7. Distribute Minerals to pregnant women 8. Project Reports; 4. Reduced nutritional anemia among 1000 CU5 and 1000 WORA. Project Monitored; PT + Consul- tant PT; Gather and Analyse Field and Hospital data Compile Field data Analyse Financial data; Month 2-8 Month 3,6,9 And 12; Quarterly Quarterly; FDCF MPMR Technical Report (TR) Financial Report (FR). Evaluation Committee - Eve Passah (Mrs) Hohoe Municipal Directorate of Health Services-Director - George Gyapong (Mr) Together Ghana (Implementing NGO) - Noah Damahasi Together Ghana (Implementing NGO) - Eredoglo Edgar Municipal Health Nutrition Officer, Hohoe - Paul Kotobridja (Mr) Assemblyman, Municipal Assembly, Hohoe

Part III Project Operational Capacity & Sustainability

3.1 Project Operational Capacity

3.1.1 Partners Level of involvement in the Project

List of Partners: 1. Hohoe Municipal Assembly-Community entry/sensitization, distribution of items and evaluation of project workings. 2.Hohoe Municipal Health Directorate-Community sensitization, training and administration of complementary food, Vitamins and Minerals and data analysis.

3.1.2 Past Experiences in the Subject Problem Area

A similar project “Maternal and Child Health Education” funded by Feed the Minds UK was carried by the team in 2007-2008. The project main features include, nutrition education, referral of pregnancy related complications, anti-natal and post natal services and Child Welfare Clinical services among others. During the project 20 TBAs and community safe motherhood educators were trained to educate women on maternal and child health issues and to refer pregnant women to the health facility for medical examination. Over 3000 women were directly reached by the project as they retained information on the importance of seeking clinical services when pregnant and after delivery and this has contributed to the increase of number of pregnant women and nursing mothers attending anti-natal, post natal and Child Welfare Clinics. The following personnel’s will bring to the project over 10 years unique expertise and experience from various fields. They include: 1. Eve Passah(Mrs) the project consultant has over 10 years as practicing Mid-wife and a public health nurse, Noah Dumahasi project officer also has over 10 year health education related project management and implementation expertise and George Gyapong(Mr)- Project Accountant equally has over 10 years working expertise in related field.

3.2 Past Experiences in the Subject Problem Area

Municipal Health Directorate (MHD) as key project partner and in line with Governments policy will continue the project. Together Ghana (TG) would update grant donors periodically on progress of sustainability. At the institutional level (TGs) Field Officers will continue to support the communities in nutritional education since TG will continue to carry out other interventions in the target communities. At the financial level TG will continue to source financial support from other institutions including the Government and private institution to continue.

PART IV Warranties and Ethical Consideration

TG shall be responsible for all risks resulting, directly or indirectly, from the storage, use, application or disposal of the supplements and undertakes to ensure that intakes of vitamins and minerals will not exceed the internationally recommended dosage.

PART V Project Budget & Justification

Budget Table 1

| Category | Breakdown Item | Unit Cost Dollars | Unit | Total Cost Dollars |
| --- | --- | --- | --- | --- |
| Operation | Community mobilization | 75.00 | 20 Comm. | 1,500 |
|  | Training /IEC materials | 62.50 | 40 groups | 2,500 |
|  | Complementary food | 62.50 | 40 groups | 10,000 |
|  | Distribution of Goods | 50.00 | 40 groups | 1,500 |
|  | Monitoring & Evaluation | 37.50 | 40 groups | 1,500 |
|  | Sub-total |  |  | 17,000 |
| Travel | Consultant | 75.00 | 4 quarters | 300 |
|  | Project Manager | 50.00 | 12 months | 600 |
|  | Field Officers | 87.50 | 12 months | 1,050 |
|  | Sub-total |  |  | 1,950 |
| Personnel | Project Manager | 25.00 | 12 months | 300 |
|  | Project Accountant | 25.00 | 12 months | 300 |
|  | 2 Field Officers | 50.00 | 12 months | 600 |
|  | Sub-total |  |  | 1,200 |
| Others | Consultant | 1,000.00 | 1 | 1,000 |
|  | Communication/Office running | 25.00 | 12 months | 300 |
|  | Sub-total |  |  | 1,300 |
|  | Grand Total |  |  | 21,850 |

IMPORTANT: an explanation of each budget item to show that the costs are          reasonable and directly related to the project activities

- These costs associated with the respective categories represent the minimum in the market and is recommended for approval.

- 20 communities made up of two groups of women and children under 5 are the project targets.

CONCLUSION

We hope potential donors reading our project proposal would donate accordingly to our project to enable us maintain a permanent place on the Global Giving website so that we can raise the needed funds for our nutrition project. Please tell your friends, family members and business associates to donate to our project. We need a minimum of $4,000 donated with a minimum of 50 donors. We are therefore looking forward to your donations.

Thank you,

Noah Dumahasi

(Projects Coordinator)

November 22, 2010