### PROJECT PROPOSAL OF LATRINES

### SECTION A – ORGANISATION  DETAILS

- Date of Application: 25October   2025

- Organisation Name: Groupe Scolaire Busogo I, Saint Benoît

- Address: Busogo Sector, Musanze District, Northern Province, Rwanda

- Contact Person:

  - Name: Fr. Jean Damascène TUYISHIMIRE

  - Position: Head Teacher

  - Phone: +250 785 010 182

  - Email: nahum990@yahoo.fr

- Legal Status: Registered Educational Institution

- Year Established: 1957

- Number of Beneficiaries:

  - Students: 2,372

  - Teachers: 57

  - Support Staff: 11

  - Total: 2,440 people

### SECTION B – PROJECT OVERVIEW

Project Title:
Construction of 24 New Latrines and Renovation of 20 Old Latrines to Improve Hygiene at G.S. Busogo I

Project  Location:
Busogo Sector, Musanze District, Northern Province, Rwanda
(12 km west of Musanze town; 115 km from Kigali)

Project Duration:
4 months (July– October 2025)

### SECTION C – PROJECT BACKGROUND

G.S. Busogo I is a rural Primary and Secondary school serving over 2,400 students and staff. The existing sanitation infrastructure is severely strained due to a growing student population. Most of the current latrines are in poor condition, unhygienic, and no longer sufficient for the number of users. This has increased the risk of disease outbreaks, absenteeism, and reduced dignity, especially for girls. There is an urgent need to construct 24 new latrines

### SECTION D – OBJECTIVES & BENEFICIARIES

Overall Goal:
To improve hygiene, health, and dignity at G.S. Busogo I by expanding and upgrading sanitation infrastructure.

Specific Objectives:

- Construct 24 new ventilated improved pit latrines to accommodate the rising number of students

- Renovate 20 old and damaged latrines to restore their usability

- Provide gender-segregated, safe, and clean toilets

- Reduce absenteeism due to sanitation-related illnesses, particularly among girls

- Promote hygiene education through student WASH clubs

Direct Beneficiaries:

- 2,372 students

- 57 teachers

- 11 supporting staff

Indirect Beneficiaries:

- Families of students (approx. 1,500 people indirectly benefit through reduced disease transmission)

### SECTION E – EXPECTED OUTCOMES

- 24 newly constructed, safe, and accessible latrines in use

- Improved sanitation practices across the school community

- 50% reduction in absenteeism due to hygiene-related illnesses (based on school health data)

- Improved retention and performance, especially for female students

### SECTION F – IMPLEMENTATION PLAN

| Activity | Timeline | Responsible |
| --- | --- | --- |
| Feasibility study and latrine design | December 2025 | School + Local Engineer |
| Community mobilization & procurement | December 2025 | School + Procurement Committee |
| Construction of 24 latrines | December 2025 | Construction Contractor |
| Renovation of 20 old latrines | December 2025 | Renovation Team |
| Hygiene promotion workshops | December 2025 | WASH Club + Teachers |
| Final inspection & reporting | December 2025 | School Team + Local Authorities |

### SECTION G – BUDGET SUMMARY

| Item | Quantity | Unit Cost (€) | Total (€) |
| --- | --- | --- | --- |
| Feasibility Study & Engineering Plans | - | 400 | 400 |
| Construction of 24 VIP Latrines | 24 units | 600 | 14,500 |
| Renovation of 20 Existing Latrines | 20 units | 200 | 2,000 |
| Materials (cement, doors, slabs, pipes) | - | - | 2,000 |
| Labor (construction + renovation) | - | - | 1,000 |
| Hygiene Promotion Materials & Training | - | - | 960 |
| Total Estimated Cost |  |  | 20860 |
| Funding Requested from Donor |  |  | 20,860 |

### SECTION H – SUSTAINABILITY

- Maintenance will be done by a School Sanitation Committee including teachers and students

- Training for cleaners and peer educators will ensure ongoing cleanliness

- The school will allocate part of its operational budget for repairs

- Community ownership will be enhanced through local labor participation

### SECTION I – MONITORING & EVALUATION

Monitoring Tools:

- Construction site visit reports

- Hygiene club feedback logs

- Student absenteeism records

- Photo documentation

Evaluation:

- Midline review after latrine construction

- Final report to donor with before/after data

- Ongoing monitoring every school term

### SECTION J – DECLARATION

I hereby confirm that the information provided above is true and accurate, and that this project is a genuine and urgent need of the school community.

Name: Fr. Jean Damascène TUYISHIMIRE
Position: Head Teacher
Date: 16 Octomber  2025