# Name of Project:	     	Train Rural Women in Self-Injection FP Methods Now

# Name of organization:   	Peace Foundation

## Postal Address:	    	House no.151 Pak Colony Umerkot Road Mirpurkhas

## Contact #: 		    	03332950775

## Website:		    	 www.peacepak.org

## Email:			    	 p_foundation@yahoo.com / peace.foundationpf@gmail.com

## Application for District:  	Kzarachi

## Duration:		      	12 months

## Date of Submission:                23rd May  2026

Back Ground:

Karachi districts  of Sindh are backward in reproductive health services provision. Many women and young girls face serious difficulties in getting modern family planning methods like DMPA-SC (Sayana Press). These problems are caused by lack of knowledge, social and cultural stigma, myths, and the absence of women-friendly and private health services.

DMPA-SC self-injection (SI) is a new and easy method that allows women to give themselves a contraceptive injection every three months. It gives women more control over their health and can be done in privacy. But in these areas, many people still don’t know about it, and not enough young people are involved in spreading awareness. Also, the health system doesn’t have enough trained staff or a strong supply chain to provide this service properly.

To solve these problems, a detailed project was started in the three districts to both increase demand for DMPA-SC SI and make sure the supply is available. The project trained youth ambassadors and peer educators to spread correct information in their communities. It also formed family planning groups at the village level to talk about common myths, report supply problems, and encourage open discussions about self-injection

2. On-Ground Engagement & BTL Activities

Peace Foundation will deploy localized, trusted, and participatory methods for driving awareness and adoption: Following are key points:

### I: .Mobile Health Camps & Rickshaw-Based Advocacy

### Purpose of the Initiative: The initiative aims to increase awareness and acceptance of DMPA-SC (Sayana Press) self-injection (SI) among women and men. We seek to build women's confidence through mobile health camps and rickshaw based advocacy in adopting and safely using SI through trusted, in-person counseling, live demonstrations, and continuous public engagement.

Location: The intervention will be implemented across Mirpurkhas targeting both rural and peri-urban communities with low contraceptive uptake.

### Strategy and Implementation Approach:  The strategy includes organizing branded mobile health camps and deploying pictorially branded auto-rickshaws as mobile advocacy units. Trainers during mobile camps will demonstrate the use of DMPA-SC using anatomical models (injection dummies), and distribute flipbooks, brochures, and starter kits. Community engagement will be done in high-traffic public spaces to spark conversations and normalize SI.

### Key Activities and Outreach Tools: Each location will host one mobile health camp bi-monthly  with over 60 participants. These camps will offer live demonstrations of self-injection, on-site counseling, and distribution of educational materials. Every six months, 100 branded auto-rickshaws will be mobilized to display SI advocacy banners with visual messages about Sayana Press, raising awareness through frequent visibility across communities.

### Timeline and Frequency of Interventions: One health camp will be conducted per month per district to ensure sustained outreach. The advocacy rickshaws will be refreshed every six months to maintain visibility and momentum.

### Delivery Strategy: Trained healthcare providers and facilitators will conduct live demonstrations and counseling during camps. Auto-rickshaw drivers, local influencers, and community champions will support ongoing visibility and promote SI messaging through mobile banners and public dialogue.

### II:. Cultural Storytelling & Entertainment for SI Awareness

### Purpose: The purpose of these creative interventions is to dispel myths and misconceptions around DMPA-SC self-injection (SI), normalize its use, and leverage local entertainment forms to deliver accurate, relatable, and culturally appropriate DMPA-SC (SI) education. By embedding SI messaging into traditional storytelling, the initiative aims to foster positive behavior change and community acceptance.

### Location:  Activities will be carried out in public spaces such as village Otaqs, local marketplaces, mela/festival grounds, shrine gatherings, and mobile community setups across rural and peri-urban areas of Mirpurkhas District and surrounding regions.

### Key Activities: We propose an annual series of culturally resonant performances per district, including: 4 street theatre plays using live drama and interactive dialogue 2 folk music sessions featuring traditional songs adapted with SRHR themes 4 short films showcasing real-life inspired stories of women choosing SI Puppet shows specifically designed to engage youth and younger audiences Short films will be projected using portable screens and solar-powered projectors. Puppet shows will cater to youth and mixed audiences. Post-performance discussions and Q&A sessions will promote audience interaction, feedback, and referrals for SI services.

### Timeline and Frequency of Interventions: Activities will be scheduled around community events, local festivals (melas), and shrine gatherings capitalizing on large gatherings and cultural momentum to reach diverse and sizeable audiences.

### Delivery Strategy: The performances will be delivered by trained local artists, puppeteers, folk musicians, and storytellers who have been sensitized on SRHR, DMPA-SC, and key messaging around self-injection. Their cultural credibility and familiarity with local dialects will enhance impact and audience trust.

### III. Public Space Activations

## III.a Village Bazaars & Pharmacies Engagement

### Purpose: To normalize conversations around DMPA-SC (self-injection) in everyday public spaces by leveraging the trust-based relationships that vendors and pharmacists have with their customers. This outreach aims to expand awareness among both women and men in non-clinical, familiar settings.

### Locations: Five branded Self-Injection (SI) information kiosks will be placed in high-traffic roadside stalls and market centers across Mirpurkhas District, targeting spaces with strong footfall and community presence.

### Timeline and Frequency of Interventions: This activity will take place during 2 seasonal bazaars and peak market days, aligning with times of highest community activity to ensure broad exposure and outreach.

### Key Actors and Collaborators: Outreach team will led by the campaign, the initiative will involve local pharmacists, stall owners, and market organizers, all of whom will be oriented to become advocates and informal referral agents for SI services.

### Delivery Strategy: Branded information kiosks will be equipped with flipbooks, banners, and posters featuring accurate and engaging SI messages., Brochures and safety leaflets will be distributed to both pharmacies and market visitors. On-the-spot counseling and Q&A support will be provided by trained outreach staff at kiosks. Pharmacists and vendors will be trained and encouraged to act as informal referral agents, directing interested individuals to nearby Lady Health Workers (LHWs) or local SI support providers.

## III.b II. Beauty Parlors & Tea Shops Awareness Outreach

Purpose: To leverage the social and conversational nature of beauty parlors and tea shops spaces where people feel comfortable and connected to promote peer to peer learning and informal dialogue around self-injection (DMPA-SC), especially among hard-to-reach men and women.

### Location: In the rural town of Mirpurkhas, the campaign will work with 5 beauty parlors  frequently visited by women. 25 tea shops that serve as community hubs for male patrons and local influencers

Timeline and Frequency of Interventions: This activity will be implemented continuously throughout the campaign period to ensure consistent visibility and message reinforcement across all social spaces.

### Key Actors and Collaborators: The effort will be carried out in collaboration with beauty parlour owners, tea shop keepers, and their regular patrons. These informal stakeholders will play a key role in creating supportive spaces for reproductive health conversations.

### Delivery Strategy: Train 5 parlor and 25 tea shop owners to display educational materials and initiate appropriate conversations about SI. Place banners, posters, and brochures in high-visibility spots (mirrors, walls, tables). Provide Information, Education, and Communication (IEC) materials for shopkeepers to distribute to interested clients discreetly and respectfully.

### VI. Community-Based Health Workforce Mobilization

## V. Frontline Health Providers as Self-Injection (SI) Ambassadors

### Purpose

This intervention aims to leverage the influence and trusted status of frontline health providers—Lady Health Workers (LHWs), midwives, Lady Health Visitors (LHVs), Traditional Birth Attendants (TBAs), and informal healthcare providers to promote the safe and informed adoption of self-injection (DMPA-SC). These providers are deeply embedded in rural and underserved communities and are viewed as reliable sources of health information, especially by women. Their direct involvement enhances message credibility, enables personalized counseling, and fosters community-level behavior change.

### Location: The activity will be implemented in the district of Mirpurkhas. Outreach will occur through home visits, at local health posts and centers, and within community gathering spaces such as markets and women’s social groups.

### Timeline and Frequency of Interventions: Each year, four technical training sessions will be conducted one per quarter. These sessions will build the knowledge and skills of the 60 selected providers and ensure continuous support for their roles as SI ambassadors throughout the year.

### Delivery Strategy: The providers will be trained in DMPA-SC counseling techniques, demonstration methods, and strategies for addressing common myths and misconceptions. Each participant will receive a starter kit, visual job aids, flipbooks, and referral tools to enhance their community engagement efforts. Furthermore, providers will be equipped with tracking and reporting tools to monitor their outreach and impact. The implementation will be supported by experienced master trainers and monitoring teams, ensuring consistent quality of training, effective knowledge transfer, and timely supervision. The intervention will empower frontline workers to become proactive champions of self-injection within their own communities.

## VI. Couples Counseling and Male Engagement Sessions

### Purpose: This intervention seeks to foster shared reproductive decision-making by engaging men and couples directly in conversations around self-injection (DMPA-SC). In many patriarchal settings, men's attitudes significantly influence women's health behaviors. By involving them in a respectful, informed dialogue, the program aims to reduce gender-based myths and resistance, build acceptance, and promote mutual support for SI adoption.

### Location: Sessions will be conducted in community halls, tea shops, mosques, or any other culturally acceptable spaces where men gather comfortably. These venues ensure accessibility and cultural appropriateness for male participation.

### Timeline and Frequency of Interventions: The intervention will include four sessions per year, delivered through community meetings, men’s gatherings, or during scheduled outreach events.

### Delivery Strategy: The sessions will be facilitated by 6 trained male educators who are well-equipped to engage other men in respectful, open conversations. Each session will include the use of visual tools, storytelling, and real-life testimonials to create relevance and trust. Educators will challenge prevalent myths in a non-confrontational manner, promoting a supportive atmosphere for reflection and discussion.

### Performance Matrix

| C | Indicator | Means of Verification | Frequency | Responsible Person(s) | Notes/Remarks |
| --- | --- | --- | --- | --- | --- |
| 1 | Number of community members reached through Mobile Health Camps and Rickshaw-Based Advocacy | Attendance registers, activity logs, photos, rickshaw GPS logs | Monthly | Outreach Supervisor, Field Coordinator | Ensure rickshaws rotate through different areas for wider coverage |
| 2 | Number of cultural performances conducted and estimated audience size | Event reports, participant estimates, photo/video documentation | Quarterly | Cultural Engagement Lead, M&E Officer | Use community feedback tools post-event (e.g., short polls or interviews) |
| 3 | Number of SI kiosks/pharmacies engaged and acting as referral points | Training attendance sheets, vendor commitment forms, referral logbooks | Bi-monthly | Market Mobilizer, Vendor Engagement Officer | Conduct spot-checks to confirm display of materials and referral practices |
| 4 | Number of health providers trained and conducting outreach (LHWs, TBAs, LHVs, etc.) | Training attendance, outreach tracking tools, visit checklists | Quarterly | Health Workforce Trainer, LHW Supervisor | Include refresher training if drop-off in outreach is observed |
| 5 | Number of peer education sessions conducted and youth reached | Session reports, attendance sheets, photos, pre/post tests | Monthly | Youth Engagement Coordinator, Peer Educators | Consider collecting testimonials and tracking gender distribution |
| 6 | Number of women participating in support circles and % reporting increased confidence in SI | Facilitator logs, participant forms, confidence self-assessments | Bi-monthly | Female Peer Leaders, LHWs | Use simple evaluation forms to assess change in knowledge and attitude |
| 7 | Number of male & religious/tribal leaders engaged and endorsements secured | Training attendance, signed support statements, meeting notes | Semi-annually | Male Engagement Lead, Religious Affairs Coordinator | Document any speeches, public endorsements, or quotes for advocacy use |

Peace Foundation Profile:

Credentials: List of key clients, major projects, and business handled during 2023-2025

| Project Sector | Project Title | Funding Amount | Duration | Donor | District(s) | Project Status (completed /Ongoing) |
| --- | --- | --- | --- | --- | --- | --- |
| Reproductive Health | To support vulnerable populations with support and information related to reproductive health and services in Balochistan. | PKR 7,800,000.00 | 1st March, 2025 28th February, 2026 | MSF Netherlands. | Dear Akkagyar and Dera Murad Jamli Blaochistab | Ongoing |
| Reproductive health | Post abortion Contraception and sensitization Pharmacy store in Tando Allahyar and Hyderabad | 12500 USD | 15 May to 30 June 2025 | IPAS- Pakistan Office | Tando Allahyar and Hyderabad | On going |
| Health and Hygiene | Reproductive Health Education for Worker Women in Non-Formal Sectors in Sindh | USD 45000.00 | 9th June, 2022 8th June, 2025 | Global Fund for Women | Mirpurkhas Tharparkar and Sanghar | Completed |
| Budget AdovacyDMPA-SC (SI) | to run a budget advocacy campaign aimed at influencing policy makers, health officials, and the Provincial Health Minister to allocate adequate funds towards training, procurement, media advocacy, and use of DMPA-SC as a family planning option | USD $146,982. | 1st January,2024, 30 June, 2025 | Clinton Health Access Initaitive | Karachi | Completed |
| Reproductive Health- DMPA-SC (SI) | Community Self-managed Menstrual Regulation with pills in Sindh Pakistan. | CAD$ 249993 | 1st January,2021 31st December,2022 | Grand Challenges Canada Fund | Mirpurkhas, Tharparkar, Hyderabad, and Nawabshah | Completed |
| Reproductive Health and Family Planning | covid-19 recovery needs of women and girls | PKR: 1237250 | 1st January,2021 31st March,2021 | OXFAM | Mirpurkhas | Completed |
| Reproductive Health and Family Planning | Reach rural women and girsl with consultation and services of safe medical abortion and family planning in south sindhpakistan | $ 179,015.00 | 1-Oct-22 30-Sep-2023 | Safe Abortion Action Fund IPPF | Tharparkar and Mirpurkhas | Completed |
| Health | Applying social accountability tools to ensure SRH services in 20 local hospitals in Sindh Pakistan. | € 38,500.00 | 1-June-22 31-May-2023 | AmplifyChangeUk | Karachi | Completed |

Team Structure: Names, roles, experience, and responsibilities of team members assigned to this project

#### 1. Program Manager: Ms. Tahira Bilal

Role: Lead strategy development, stakeholder coordination, team supervision, and overall program oversight.

Key Responsibilities:

- Develop and tailor strategies for rural/peri-urban audiences

- Ensure cultural and linguistic appropriateness of messaging

- Coordinate with donors, technical experts, and local authorities

- Supervise field teams and provide troubleshooting support

- Oversee budget and work plan implementation

#### 2. District Coordinator, One per district, Ms. Shakeela Perveen

Role: Manage daily execution of field activities, liaise with local stakeholders, and supervise field staff.

Key Responsibilities:

- Coordinate logistics for health camps, street theatre, film screenings, etc.

- Liaise with community leaders, local influencers, and venue hosts

- Ensure timely implementation of outreach activities

- Track community engagement and mobilization metrics

#### 3. Community Mobilizer: Ms. Shama Balaoch, Ms.Najama Shaikh  and Mr, Imran Soomro

Role: Serve as frontline facilitators for awareness sessions, workshops, support groups, and interpersonal outreach.

Key Responsibilities:

- Conduct home visits, women-only and couple sessions

- Support pharmacists and LHWs in community outreach

- Distribute IEC materials, facilitate discussions in local dialects

- Collect feedback and participation data

- Create easy-to-understand messaging for various formats

- Write content for leaflets, banners, video scripts, social media

- Translate health information into local idioms and expressions

- Review and localize messaging for TikTok or influencer videos

#### 4. Monitoring & Evaluation Officer: Ms. Muhammad Farhan Rajput

Role: Oversee data collection, participant tracking, and outcome measurement for all field activities.

Key Responsibilities:

- Design M&E tools and checklists

- Compile reach numbers and feedback from community events

- Track activity implementation against timelines and goals

### 5. Support Staff

#### Logistics Assistant: Mr. Meer Khan

Role: Provide transportation support for staff, supplies, and mobile outreach units (e.g., rickshaws or branded buses).

Key Responsibilities:

- Take high-quality photos/videos during field events

- Compile participant stories and quotes

- Maintain organized activity logs and media archives

- Drive staff and equipment to field locations

- Help with logistics setup and breakdown at events

- Ensure timely delivery of IEC materials and branding items

References: Contact details of at least three clients for reference checks

| *Sr. | Donor Organization | Focal Person in Donor Org. | Contact Number | Contact Email | Office Address |
| --- | --- | --- | --- | --- | --- |
| 1 | Medicine Sans Frontier Netherlands | Noor Rijinberg: = : | +31 629504681 | Noor.Rijnberg@amsterdam.msf.org | Netherland |
| 2 | IPAS-Pakistan | Ms, Ayesha Salma Kariapur | 03088877719 | salmaa@ipas.org | Islamabad |
| 3 | Clinton Health Access Initiative USA | Chloe Legaspi-Cavin clegaspicavin@clintonhealthaccess.org Contracts Department | +1 617-774-0220 | contractsdepartment@clintonhealthaccess.org | 383 Dorchester Avenue, Suite 400, Boston, MA 02127 USA |
| 4 | Grand Challenges Canada | Diana Sanchez Guadarrama, email | T+1.416.583.5821 | info@grandchallenges.ca diana.sanchez@grandchallenges.ca | MaRS Centre.West Tower 661 University Avenue. Suite 1720 Toranto. Ontario. Canada M5G 1M1 |

| WORK PLAN TABLE |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Activity Area | Key Activities | Location | Timeline & Frequency | Delivery Strategy | Key Actors |
| I. Mobile Health Camps & Rickshaw-Based Advocacy | Conduct monthly mobile health camps with live DMPA-SC SI demonstrations | Rural & peri-urban Karachi | One camp per month per district | Trainers provide SI demonstrations using anatomical models | Health trainers, rickshaw drivers, local influencers |
|  | Rickshaw-based advocacy using 100 branded auto-rickshaws every six months |  | Rickshaw banners refreshed every 6 months | Rickshaw drivers and influencers promote SI messages publicly |  |
|  | • Distribution of flipbooks, brochures, SI starter kits |  |  |  |  |
| II. Cultural Storytelling & Entertainment for SI Awareness | Annual street theatre (4 plays) | Village Otaqs, markets, melas, shrines, public spaces | Scheduled around festivals, local gatherings, and melas | Local artists integrate SI messaging into dramas and songs | Folk artists, puppeteers, storytellers, SRHR facilitators |
|  | Folk music sessions (2 per year) |  |  | Portable screens & solar projectors for films |  |
|  | Screening of 4 short films on SI stories |  |  | Facilitators guide Q&A discussions |  |
|  | Puppet shows for youth |  |  |  |  |
|  | Post-performance discussions & Q&A |  |  |  |  |
| III.a Public Space Activations – Village Bazaars & Pharmacies | Install 5 branded SI kiosks | Markets, roadside stalls, pharmacies | 2 seasonal bazaars per year | Display SI posters, banners, brochures | Pharmacists, stall owners, outreach teams |
|  | Outreach during 2 seasonal bazaars & peak market days |  | Continuous presence at kiosks during peak days | On-spot counseling by outreach staff |  |
|  | Train pharmacists and vendors as informal SI referral agents |  |  |  |  |
| III.b Beauty Parlors & Tea Shops Awareness Outreach | Engage 5 beauty parlors & 25 tea shops | Selected rural & peri-urban areas in Darsano Chanoo Karachi | Continuous implementation throughout campaign period | Posters on mirrors/walls; brochures given discreetly | Parlor owners, tea shop keepers, outreach educators |
|  | Display SI materials in shops and parlors |  |  | Shopkeepers initiate safe conversations |  |
|  | Train owners to facilitate SI conversations |  |  |  |  |
| IV. Community-Based Health Workforce Mobilization (SI Ambassadors) | Train 60 LHWs, LHVs, midwives, TBAs on SI counseling | Homes, health posts, community centers | 4 trainings per year (one per quarter) | Master trainers provide SI technical training | LHWs, LHVs, TBAs, master trainers |
|  | Provide job aids, flipbooks, referral tools |  |  | Providers conduct home visits and community counseling |  |
|  | Quarterly refresher sessions |  |  | Use tracking tools to report activities |  |
| V. Couples Counseling & Male Engagement Sessions | Conduct 4 annual male engagement sessions | Tea shops, mosques, community halls | 4 sessions per year | Male educators lead respectful group dialogues |  |
|  | Use visual tools, storytelling, testimonials |  |  | Build supportive attitudes toward SI and women’s autonomy |  |
|  | Address myths and promote joint decision-making |  |  |  |  |

Budget

|  | Budget |  |
| --- | --- | --- |
| Self-Injection (DMPA-SC) Awareness, Training & Community Engagement Campaign – Mirpurkhas” |  |  |
| 1. Mobile Health Camps & Rickshaw-Based Advocacy — USD 4,100 |  |  |
| Line Item | Cost (USD) | Description |
| Mobile Health Camps (12 camps per year) | 2,400 | Venue setup, mats, water, transport, demo supplies; approx. $200 per camp. |
| Rickshaw-Based Advocacy (100 rickshaws every 6 months) | 1,200 | Printing of banners, stickers, SI visuals; honorarium for display. |
| Training Supplies for Demonstrations | 500 | Purchase of injection models, flipbooks, brochures, starter kit samples. |
| Subtotal: 4,100 USD |  |  |
| 2. Cultural Storytelling & Entertainment for SI Awareness — USD 3,000 |  |  |
| Line Item | Cost | Description |
| Street Theatre (4 plays) | 1,000 | Artist fees, costumes, sound system rental, transport. |
| Folk Music (2 sessions) | 400 | Musicians’ fees and transport; adaptation of songs with SRHR messaging. |
| Short Films Production & Screening | 1,000 | Film shooting, editing, voiceover, portable projector rental. |
| Puppet Shows (Youth Engagement) | 600 | Puppeteer fees, props, travel; youth-friendly SI storytelling. |
| Subtotal: 3,000 USD |  |  |
| 3. Public Space Activations – Bazaars, Pharmacies, Parlors, Tea Shops — USD 2,300 |  |  |
| Line Item | Cost | Description |
| 5 Branded SI Information Kiosks | 800 | Kiosk design, printing, chairs, banners, posters, IEC packs. |
| Outreach in Seasonal Bazaars & Peak Market Days | 600 | Mobilization, booth materials, staff travel. |
| Beauty Parlors (5) & Tea Shops (25) Engagement | 500 | Printing, posters, mirror stickers, brochures. |
| Orientation for Pharmacists & Vendors | 400 | One training session; refreshment, IEC materials, facilitator time. |
| Subtotal: 2,300 USD |  |  |
| 4. Community Health Workforce Mobilization — USD 3,500 |  |  |
| Line Item | Cost | Description |
| Training for 60 LHWs/LHVs/TBAs (Quarterly Sessions) | 2,200 | Venue, refreshments, trainer fees, job aids, transport reimbursement. |
| Starter Kits & Flipbooks for Providers | 800 | Visual tools, counseling aids, SI referral cards. |
| Monitoring & Reporting Tools | 500 | Registers, supervisor travel, mobile data for reporting. |
| Subtotal: 3,500 USD |  |  |
| 5. Couples Counseling & Male Engagement Sessions — USD 1,100 |  |  |
| Line Item | Cost | Description |
| 4 Male Engagement Sessions | 700 | Venue, refreshments, educator honorarium, visual tools. |
| Development of Male-Friendly IEC Materials | 400 | Posters, dialogue cards, myth-busting flyers. |
| Subtotal: 1,100 USD |  |  |
| 6. Project Management & Administration — USD 900 |  |  |
| Line Item | Cost | Description |
| Project Coordinator (Part-Time) | 500 | Coordination of activities, reporting, stakeholder engagement. |
| Transport & Field Allowances | 300 | Fuel, local transport for staff. |
| Communication & Printing | 100 | Phone calls, photocopying, WhatsApp dissemination. |
| Subtotal: 900 USD |  |  |
| TOTAL PROJECT BUDGET: 14,900 USD |  |  |
| (Within the 15,000 USD limit) |  |  |
| Budget Summary Table |  |  |
| Budget Category | Amount (USD) |  |
| 1. Mobile Camps & Rickshaw Advocacy | 4,100 |  |
| 2. Cultural Storytelling & Entertainment | 3,000 |  |
| 3. Public Space Activations | 2,300 |  |
| 4. Health Workforce Mobilization | 3,500 |  |
| 5. Male Engagement Sessions | 1,100 |  |
| 6. Project Management & Admin | 900 |  |
| Total | 14,900 USD |  |