Potatoes for Peace Proposal

1. Potatoes for Peace is among projects that focused on an Agri-Value Chain for Youth Ex-Rebels' Reintegration, Women's Resilience, and Cross-Border Trade in the Great Lakes region, addresses several critical needs at once.

2. Goal: To contribute to sustainable peace and economic stability in Masisi Territory through inclusive agricultural development (Potatoes- Value chain) and cross-border trade.

3. Specific Objectives :

  - Reintegration: By the end of the project, successfully enroll and retain 100 youth ex-combatants in the project, achieving an 70% decrease in reported attempts to rejoin armed groups among participants.

  - Empowerment: By the end of the project, increase the average annual income of 150 vulnerable returnee IDPs women beneficiaries by 65% through participation in the potato value chain.

  - Production: By the end of the project, cultivate a minimum of 10 hectares of potatoes, yielding an estimated 300 metric tons for local and cross-border markets. (300 tons x 300$ = 90.000$)

  - Trade: By the end of the project, establish one functional trade partnership for cross-border sale of processed or raw potatoes to a neighboring Great Lakes country (e.g., Rwanda or Uganda).

## 4. Estimated Budget

| Category | Item | Quantity/Area | Estimated Cost (USD) |
| --- | --- | --- | --- |
| Land & Prep | Renting of Fertile Land | 10 Hectares (for 1-2 seasons) | 5.000$ |
|  | Land Clearing & Plowing | 10 Hectares | 1.000 $ |
| Inputs | Certified Potato Seeds | 30 tons | 9.000$ |
|  | Fertilizer & Pesticides |  | 2.000$ |
| Training | Agricultural Skills Training | 250 Beneficiaries × 2 sessions | 3.000$ |
|  | Business/Market Training | 250 Beneficiaries × 2 sessions | 3.000$ |
| Tools & Equipment | Basic Farming Tool Kits | 250 Kits | 2.500$ |
|  | Storage/Warehouse Rental | 1 Unit | 1.000$ |
| Staffing & Admin | Project Manager, Agronomist, Social Worker | 12 Months | 12.000$ |
| Total |  |  | 38.500$ |

## 5. Value Chain Integration

The Value Chain is the key to sustainability beyond the initial harvest.

- Upstream (Input Supply):

  - Sourcing: Secure reliable, high-quality, disease-free certified potato seeds (Crucial for Masisi).

  - Training: Focus the agricultural training on best practices for high-yield, disease-resistant varieties suitable for the Great Lakes market.

- Midstream (Processing):

  - Value Addition: Propose simple processing (e.g., grading, washing, simple drying, or chip-making) to increase profit margins and extend shelf life. This is a great activity for the women's cooperatives.

- Downstream (Market Access):

  - Local Markets: Partner with local markets and institutions for bulk sales.

  - Cross-Border Trade: Identify specific buyers/cooperatives in neighboring countries and establish a formal, legal trade mechanism. Focus on market demand—what potato varieties are most desired in Goma, Kigali, or Kampala.

Prapared by:

- Mr Leon Simwerayi, AJVDC Brigade Verte, National NGO, Goma/ DRC

- Revende Esther LOLA, Partnership and Projects Manager, Catholic University LA SAPENTIA/Goma

- Mrs Olive Kamara, COSOC – GL/ Kigali – Rwanda

Tel: +243 992570911, Email: peace4africa1@gmail.com