Proposal to Establish STEAMshala to Improve the Learning Levels of Underserved studying in Govt school/Aided in Bangalore

Submitted to:

Submitted by:

Samarthanam Trust for the Disabled
Bangalore

## Summary of the Project

| Title of the Project | Proposal to Establish STEAMshala to Improve the Learning Levels of Underserved studying in Government school in Bangalore |
| --- | --- |
| Location of the Project |  |
| No of Schools | 1 Govt School |
| Project Duration | 1 year |
| Project Beneficiaries |  |
| Budget Required | INR 1738728 |

I.Organisation

Samarthanam Trust for the Disabled, since its inception, has been empowering persons with disabilities and the underserved in socio- economic – cultural fronts through its various initiatives on Education, Livelihood, Environment, Health and Nutrition, Sports, Arts and Culture and Rehabilitation. Samarthanam works with People with disabilities (PwDs) and persons from underprivileged communities in 18 locations across the Country.

The organisation was established in the year 1997 by Founder Managing Trustee, Dr. Mahantesh G Kivadasannavar along with his school mate and childhood friend, Late Nagesh SP. Samarthanam has brought about positive changes in the lives of millions of people with disabilities and the underprivileged communities across various fronts.  Samarthanam is affiliated to the World Blind Union and is one of few non-profits to receive Special UN Consultative Status in the year 2015.

Samarthanam’s programme also emphasis on creating and strengthening Ecosystem development by capacitating   parents, teachers and govt frontline workers. Apart from this, ushering technology in large number of schools for accessing quality education is one of the priority areas for Samarthanam organisation. Samarthanam’s work has received wide acclaim and honoured with recognitions and awards. The following are some of the recognitions received in the last 3 decades.

| National Awards | State Awards | Special Awards | Television Awards | Industry Awards |
| --- | --- | --- | --- | --- |
| Child Welfare in the year 2010 and 2014 NAB Sarojini Trilok Nath National Award in the year 2018 | By Govt of Karnataka in 2013, Andhra Pradesh and Telangana in the year 2018 and 2019 respectively | NCPEDP Shell Helen Keller Award 2013 Spirit of Humanity Award 2015 | CNBC TV Award-Indian Business Leaders Award in 2018 NDTV Spirit of Sports Award in the year 2012 | NASSCOM Award 2016 Cavin Care Ability Awards in the year 2018 |

II. Rationale

There has been paradigm shift in the teaching methodology in the classrooms in select schools with proactive packaging of STEM, Technology Tinkering Labs and Digitalisation of Classrooms across the country. This trend has emerged due to challenges faced by schools during covid pandemic after online teaching method emerged as the sole alternative medium for teaching during the closure of schools.

The current status is students from marginalised sections, children with disabilities and children studying government schools lose out on the opportunity to study STEM (Science Technology Engineering and Mathematics) in classrooms. The result is they don’t pursue these subjects as career options. Often learners from marginalized sections, especially girls and learners with special needs, are underrepresented and do not get a chance to voice their thoughts and ideas in the classroom.

STEAM Framework has been developed to overcome the obstacles, barriers and comprehension of STEM subjects for persons from underserved communities particularly, persons with disabilities. Arts was included in STEAM with objective to showcase the problem solving ability, creativity through music, performance based voice, theatre and marketspace hands-on activities. There are positive learning outcomes associated with arts and STEM integration, such as increased critical thinking abilities, higher order thinking and deeper learning, content mastery, creative problem solving, team work and communication skills, improved reasoning, general engagement and enjoyment of learning.

III. Samarthanam’s STEAMshala Project

Samarthanam Trust for the Disabled, as coined STEAM approach as STEAMshala, to enhance the quality learning outcomes for the students with disabilities and non-disabled students from the underprivileged communities. The STEAMshala adapts a methodology for understanding “STEM Concepts” through a fun learning methods for the benefit of underserved communities. In otherwords, it’s a methodology for students for stimulating imagination, understanding concepts through “Do It Yourself (DIY)”, “Hands on Experience”, Quiz, Painting etc., with help of technology tools and by trained teachers. This fosters participatory learning among the students to improve their learning curve and promote inclusion in the long run.

The project has three components : -
(i)    Upgradation of classroom with STEAM’s tools and exhibits.
(ii)   Capacity Building for Teachers.
(iii)   Implementing STEAM’s Methodology and integration into curriculum

The project will be covered in 1 government/aided school covering students (1 to 5th std) in Bangalore location in Karnataka. The timeline of the project is 1 year.

IV. Objectives

- To improve on quality of learning of STEM subjects among the underserved by adapting STEAM focusing on ART infused pedagogy/methodology.

- To capacitate the teachers in STEAM methodology through capacity building training programme and integrating into curriculum.

V. Log Frame

| Activities | Outputs | Outcomes | Impact |
| --- | --- | --- | --- |
| Infrastructure setup Upgradation of classroom with Learning Resource | 1 weeks required for implementation of STEAM in classroom with 400 sq. feet. 1 Do it yourself (DIY) kits mapped with curriculum of class 1 to 5 Do it Yourself (DIY) comprises of charts , pictures, of Human body, Animals, Plants, Alphabets, Family charts, | 80% of students with disabilities and underserved improve their learning levels and increase participation. | Child Centric Learning System in school promotes STEM Education and ensures sustainability |
| Teacher Development Programme and Curriculum Integration | 1 training extensive training programmes for primary school teacher. The training programme will deliver Knowledge and model practices to deliver STEAM Education. |  |  |
| Partnering with School Management & Development Committee (SDMC) of schools to sustain the STEAMshala | 1 monthly meeting per month for ensuring participation of SDMC support to sustain STEAMshala after exit of project | 80% of students participate and access quality education through STEAMshala and sustained through SDMC |  |

VII. Budget

| STEAM Shala Program-Primary Schools |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| CAPEX - A |  |  |  |  |  |  |
| Sl. No. | Particulars | Unit cost | No of Units | No of Months | Total | Remarks |
| 1 | STEAM Program School - for class 1-5 | 1,86,999 | 1 | 12 | 186999 | 50+ hands-on TLM + 7 informative backdrops + 1 Training Manual in vernacular language |
| 2 | STEAM DigitalShala | 93,500 | 1 | 12 | 93500 | Smart TV Android/Google 55" with 2 year warranty + Curriculum aligned offline digital content for class 1-5 in vernacular language+1.2KvA UPS+Installation |
| 3 | Installation + Classroom Infrastructure | 45,900 | 1 | 12 | 45900 | Wall Painting + Electric wiring & Plugs + 1 Almirah+2 Door banner |
| 4 | Teachers Development Program (TDP) | 44,900 | 1 | 12 | 44900 | 2 day Half yearly Training + Yearlong online support |
| 5 | Monitoring & Evaluation (M&E) | 34,900 | 1 | 12 | 34900 | Half yearly - 2 visits |
| 6 | STEAM Library | 8,999 | 1 | 12 | 8999 | 100 books in vernacular language |
|  | Sub Total | 4,15,198 |  |  | 415198 |  |
|  | GST @ 18% | 74,736 |  |  | 74736 |  |
|  | Total | 4,89,934 |  |  | 489934 |  |
| OPEX - B |  |  |  |  |  |  |
| Sl. No. | Particulars | Unit cost | No of Units | Months | Total | Remarks |
| 6 | Project Manager Salary | 45,000 | 1 | 12 | 540000 | The program manager will be working throughout the program start to the end monitoring and assigning the tasks to the coordinators and also in visiting schools for monitoring and evaluation, generating the weekly, monthly, quarterly and annual reports along with testimonies and case stories of the schools and beneficiaries. |
| 7 | Coordinators - Salary & Communication Expenses | 30,000 | 1 | 12 | 360000 | The program coordinator will be working throughout the program start to the end facilitating the hassle free flow of the implemented program and the expenses will be incurred for the coordinator's travel and salary for identification of schools, permission from the education department, facilitating with the installation team and conducting school visits for monitoring the utilization of the provided resources. . |
| 8 | Travel for Program team and Coordinator | 10,000 | 1 | 12 | 120000 | The expense will be incurred towards the travel of the program manager to all the locations on a quarterly basis (every 3 months 1 location will be visited) and conduct monitoring visits, interaction with school Principals, teachers and students and collect the feedback and opinion about the implemented program. |
| 9 | Inauguration / Volunteering / Branding / Miscellaneous | LS | NA | NA | 100000 | Includes branding, inauguration, and volunteering activities |
|  | Total Cost (B) |  |  |  | 1120000 |  |
|  | Total Cost (A+B) |  |  |  | 1609934 |  |
|  | Project Implementation Cost |  |  |  | 128794.69 |  |
|  | Total Project Cost |  |  |  | 1738728 |  |

VIII. Brand Promotion

The project has good potential for branding and volunteering, as it is covering 750 students (per annum) from 5 schools in multiple locations.  Apart from this, the Eco-system comprises of 5000 stakeholders related to school and education.  As the schools have already established SMART classrooms, the contents in audio- visual can be viewed by students at classroom level.

In addition to above branding strategy, Samarthanam provides the following opportunities: -

(i)Website and other social media platforms

(ii) Annual Reports, Newsletters

(iii) Name boards or banners

(iv) Media sharing / press notes of events

XI. Volunteering Opportunities:

Volunteering activities fulfils the need and goal of building strong and self-sufficient young talent with a focused approach. Volunteers can share their knowledge and interact with a diverse group of students and teachers virtually /physically. This helps to build and strengthen a strong relationship between the under-served students and corporates and volunteering-cum-mentoring program gives volunteers a chance to become the CHANGE MAKERS.

Senior Leadership

Senior leaders will be invited to inaugurate the project.

Samarthanam works closely with media for promotions of the same (with approval from the sponsor)

Activities can be conducted by Volunteers as below:

- Volunteers will be provided with opportunities to share about critical analysis, understanding concepts and Experimenting in real-time environment, and its role in Career prospect., Also, volunteers’ inputs such as inspirational Stories on motivation, life skills or on specific personality for school children

- Volunteer teams will be provided to conduct webinar on zoom/meet in which hundreds of students will take part virtually. The volunteers can host the quiz, participate as team members and also inspire the children by telling them stories regarding the subjects.

X. Project Justification & Sustainability

Samarthanam has been implementing education projects in govt schools in various locations across the country.  The models have been tried, tested and proven by producing a critical mass of students with innovative skills in the country. The project has huge potential to scale up and also can be emulated through replication across the country.  The Projects can be sustained by enabling participation of SDMC and establishing linkage with govt and non govt stakeholders in the country

We are confident that in financial partnership with you, the above school project will be implemented in 1 govt/aided school in Bangalore