## Budget
Programe Name:Tailoring Training Programme for Youth
Organization Name: Upendo Children Kilifi CBO
Workplan Activities
| Workplan Activities | Unit | No. of Units | Unit Cost (Kes) | Frequency/Days/Months/Years | Total Kes
1 | Skilling the youth on Tailoring
1.1 | Facilitator (tailoring trainer) | pax | 1 | 20000 | 11 | 220000
1.2 | Facilitator (entrepreneurship trainer) | pax | 1 | 30000 | 1 | 30000
1.3 | Training machines - manual | pcs | 25 | 15000 | 1 | 375000
1.4 | Electric machines - electric | pcs | 1 | 40000 | 1 | 40000
1.5 | Training machines - overlock | pcs | 1 | 30000 | 1 | 30000
1.6 | Tables | pcs | 5 | 5000 | 1 | 25000
1.7 | Iron box | pcs | 3 | 3000 | 1 | 9000
1.8 | Fitting room mirror and curtain | pcs | 1 | 5000 | 1 | 5000
1.9 | Scissors | pcs | 30 | 300 | 1 | 9000
1.1 | Measuring tapes | pcs | 60 | 100 | 1 | 6000
1.11 | Other materials (fabric, brown papers, threads, zippers, buttons, etc) | set | 4 | 15000 | 1 | 60000
| Sub-Total |  |  |  |  | 809000
2 | Administration
2.1 | Water | units | 1 | 1000 | 12 | 12000
2.2 | Electricity | units | 1 | 3000 | 12 | 36000
2.3 | NITA Examination Certification | pax | 30 | 5000 | 1 | 150000
2.4 | Transport |  | 1 | 15000 | 1 | 15000
| Sub total |  |  |  |  | 213000
| Total (Kes) |  |  |  |  | 1022000
| Exchange rate used |  |  |  |  | 128
| Total Project Cost in USD |  |  |  |  | 7984.375

## Work Plan
Program Name: Tailoring Training Programme for Youth
Organization Name: Upendo Children Kilifi CBO
| Work Plan Activities | Months
|  | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12
1 | Planning Meetings & Mobilization | bar: Months Month 1
2 | Training On Tailoring Training Cohort One | bar: Months Month 2 to Months Month 11
3 | Training on Enterpernuership | bar: Months Month 12
4 | NITA Examination and Graduation | bar: Months Month 12