Description of the proposed Project

| Proposed project name: | Equipping 50 Kenyan Poor Rural Youth with Computer Skills |
| --- | --- |
| Main objective of the proposed project | Provide 50 youth with ICT training for employability and job creation |
| Specific location(s) of proposed project: | Trans-nzoia East District |
| Proposed project duration (in months): | 12 |
| Total grant amount requested | Ksh 336,000 US$ 4200 |
| Target number – how many direct beneficiaries will your project have? | 50 (At least 10 disabled youth and 20 girls) |

- (i) What is the youth need/problem/issue to be addressed by your proposed project? How was this need identified?

Lack of access to information and communication technologies has remained a major challenge to youth in the community especially in rural areas like Trans Nzoia. Youth with disability are particular left out in this technological development. Due to their disability, they are often forgotten and can not be able to travel long distances to access computer services. An area where young people have an edge is the emerging information society driven by new technologies. The youth require literacy, skills, accessibility and affordability to information and communication technologies as an important ingredient to using them to provide employment and entrepreneurial opportunities for youth Over the last three years, TYSA has had many requests for the provision of Computer literacy from its beneficiaries and other youth in the community. Internet and computer related services are on demand. There is only one internet modem in the community- which is by TYSA. This would provide an avenue for TYSA to reach and empower disabled youth in the community as this involves minimal physical energy and movement and is hence conducive for them. TYSA beneficiaries Lameck, Christine and Pascilia have shared greatly in shaping up this project. Their focus on economic empowerment of the youth has helped in making key decisions towards this project.

- (ii) What strategic document by Government or international development organizations have you looked at in identifying the issues/problems described (i) above?

The Millennium Development Goals. Goal one is to Eradicate Extreme Poverty and Hunger. Target 2: Achieve full and productive employment and decent work for all, including women and young people The Kenya Vision 2030 identifies Information and Communication Technologies as key economic stimulus especially at the community level.

- (iii) Briefly explain how the proposed project will involve and ultimately benefit youth:

15 youth in TYSA have been involved in designing this project. The project takes the youth as beneficiaries. They will also be involved in the implementation and sustainability of the project. The youth who will be trained through this project will also be engaged in production and selling of Information Communication and Educational materials. This shall provide direct employment to them. The youth with physical disability who can not participate in sports will be involved in production of materials and while at the field participate in filling in the score board for the soccer matches. They will produce fixtures of matches

- (v) Detailed Activity Plans

| Major activity | Specific Tasks | Time frame (in days or months) | Persons Responsible (by designation in the organization) | Other actors you may work with (by organization/skill areas, etc) |
| --- | --- | --- | --- | --- |
| 1. Awareness raising among potential beneficiaries | Organize one day workshop with school teachers, | One month | Lameck Nyandega- Education Coordinator Stephen Ombere- Child protection Coordinator | Area Social Development Officer |
|  | One day workshop with community leaders | One day |  |  |
|  | One day workshop with youths | One day |  |  |
|  | One day planning with TYSA stuff | One day |  |  |
| 2. Training in Information and Communication Technologies (computer proficiency, internet use and cinematography | Purchase and preparations of equipments eg computers, | 21 days | Simon Njuguna, ICT Intern Christine Osere- Training Coordinator Nancy Moraa-Volunteer and Beneficiary Monicah Ngede- Volunteer and Beneficiary | Officials from Ministry of Industrialization as well as Higher Learning, Science and Technology, ICT Board |
|  | Training in basic computer skills | 30 days |  |  |
|  | Training in internet use | 15 days |  |  |
|  | Specialized training in Design and publishing ( CorelDraw) | 14 days |  |  |
|  | Specialized training in Type setting | 7 days |  |  |
|  | Specialized training in photocopying, binding | 7 days |  |  |
|  | Specialized training in cinematography | 14 days |  |  |
| 3. Marketing of project services | Preparation and dissemination of marketing materials eg leaflets, posters | 30 days | Lameck Nyandega- Education Coordinator Stephen Ombere- Child protection Coordinator Pascilia Naloka- Community Mobilizer |  |
|  | Visiting schools, churches and market places to introduce project services | 21 days |  |  |
|  | Collating market information | 14 days |  |  |
| 4. Production of Information, Education and Communication materials | Collating customer needs | 14 days | Simon Njuguna, ICT Intern Lameck Nyandega-Education Coordinator |  |
|  | Purchase of required production materials | 14 days |  |  |
|  | Designing, production and supply of orders as per customer request | 9 months |  |  |
| 5. Provision of Library and Internet Services | Fixing the necessary infrastructure | 21 days | Lillian Wasare- Volunteer & Community Mobilizer Mercy Ipara-Volunteer &Community Mobilizer Ojiloh Osere- Football Coordinator |  |
|  | Purchase of reading materials | 14 days |  |  |
|  | Fixing the internet and Installation of DSTV | 7 days |  |  |
| 6. Monitoring and evaluation | Development of monitoring tool | 14 days | Gichuki Francis- Executive Director |  |
|  | Visiting customers | 6 months |  |  |
|  | Report writing | 4 months |  |  |

(vi) Indicators Table

Anticipated results of the project activities:

| Activity | Immediate results (outputs) | Anticipated changes resulting from the outputs (outcomes) |
| --- | --- | --- |
| Awareness raising among potential beneficiaries | - A one day workshop with 50 youths held on ICT - A one day workshop with 20 young teachers - A one day workshop with 20 community and school administration leaders on sensitization in ICT | Stakeholders support the project |
| Training in Information and Communication Technologies (computer proficiency, internet use and cinematography | - 40 youths trained in computer proficiency (At least 10 with disabilities) - 10 young teachers trained in computer proficiency - 50% take up the internship in IEC production in the project - 100% of the trainee open e-mail accounts and access internet - 5 trainees specialize in designing and publishing - 5 trainees specialize in type setting - 5 trainees specialize in binding, scanning, photocopying, lamination etc - 10 youth trained in cinematography | The youth embrace the use of ICT in job creation |
| Marketing of project services | - 10 primary and 10 secondary schools visited - 10 self help groups and community based organization visited - 20 churches visited - 200 advert posters produced and circulated | Community supports the initiative by youths |
| Production of Information, Education and Communication materials | - 600 school IDs produced - 1000 school report books produced - 200 internal exams printed - 400 sports and educational certificates printed - 1000 documents typed and photocopied - 500 copies of newsletters produced - 300 meal cards produced - 500 posters - 100 copies of programs produced - 100 cards(wedding, burial etc) | Growth, expansion and sustainability of the project |
| Provision of Library and Internet Services | - Purchase of assorted reading materials - Installation of Digital Satellite Television (DSTV) - Purchase of internet modem - Provision of infrastructure e.g. furniture | Improved educational level in the community and job creation among the youth. A culture of Reading and Research created in the community |
| Monitoring and evaluation | Quarterly project reports Photos | Lessons learnt from the project shared with stake holders and other actors in development |