## Summary Guidance (hidden)
SUMMARY GUIDANCE This workbook contains the project documents required to accompany the proposal document. For each project please complete the following: - Proposal template (in MS Word) - Logframe - Activity planning table - Budget Narrative - Results monitoring table The other sheets in this workbook are provided for your reference: - Activity monitoring template. This will auto-complete once the activity planning template has been filled out. The activity monitoring template will form the basis of reporting during the project. - Instructions. This sheet provides detailed instructions on how to complete the monitoring and planning tables.

## a - Instructions (hidden)
BTRMU Project Management Tools
Guidance for using these tools
Purpose of these tools: These tools are designed to assist in management of projects on the ground. They provide standard templates that can be used by individual projects.
Activity Planning Template:
The Activity Planning template can be used to plan for both project activities found in the logframe and functional project tasks. In general cells that have no shading (white) require data/information to be entered. Cells that are shaded grey are titles or have formulas that will automatically generate data. Field-by-field instructions: Activity indicator: list the standard activity indicators and the project specific activity indicators planned for the project. These should match those included in the approved project logframe. You may also include functional project tasks (i.e. hire staff, register beneficiaries, conduct monitoring visits, etc.) to assist in management of your project, however these are not mandatory. UOM: detail the unit of measurement for each indicator. Month (1-12): for each indicator insert the target number of activities to be conducted each month. Do not simply shade the box. For projects longer than 12 months please contact SPC for a revised template. Total Target: a formula will automatically calculate the total target for each indicator based on the values entered each month. Average monthly target: a formula will automatically calculate the average target for each indicator based on the values entered each month. Target # of beneficiaries: for each indicator insert the number of people that will benefit from this activity during the project year of implementation. Numbers should be broken down by males and females and then the total will automatically generate. Responsible officer: identify the specific person within the project team who will be responsible for conducting each activity.
Activity Monitoring Template
The activity monitoring template is linked to the planning template and many fields (shaded grey) will autocomplete based on the information entered in the activity planning template. Activity indicator, code, monthly and total target, and non-reportable total: will be copied automatically from the activity planner. The activity monitoring template will form the basis of reporting during the project. Actual: each month enter the actual number of activities completed for each indicator. If no activities have been completed for a specific indicator enter 0 rather than leaving the cell empty. % to-date achievement: these cells contains formulas that will automatically calculate what percentage of the year-to-date target has been achieved. Comment on difference: include a brief comment explaining any difference between the actual number of activities completed compared to the planned number. Beneficiary target: this will be automatically copied from the totals entered in the planning template. Beneficiaries reached THIS month: each month detail how many beneficiaries have been reached through the completed activities for each indicator. Numbers should be broken down by males and females and the total will automatically be calculated. These cells should be updated each month, the previous month's data deleted and the new data for the current month entered. Beneficiaries reached TO DATE: this column should be used to track the cumulative number of beneficiaries reached to-date by each activity. For some activities this will be a sum of all the months to date. For others it will remain constant as the same beneficiaries are reached each month.
Results Monitoring Template Guidelines
Results level: this refers to the level the result appears in the project logframe. The relevant level for each result should be selected from the list: Impact, MTO (medium-term outcome) or STO (short-term outcome). Result: the specific short-term, medium term outcome or impact that each indicator is measuring achievement off. This should match that included in the project logframe. A result should be repeated when more than one results indicator is used to measure the result. Result indicator: the actual results indicators from the SP logframe that will be used to measured. Planned: a baseline value for each indicator should be entered in the actual row. If an accurate value is not available (not yet collected) at time of planning an estimate should be given and entered in the planned row. This should be updated to an actual value in the actual row once the baseline data is collected. An end of project target should also be entered for each indicator. Benchmark values to show expected progress towards the target at defined time points should also be entered detailing the time points that the benchmarks will be measured. The frequency and number of benchmarks should be determined by each project and be detailed in the template. Actual: at the specific time points detailed by the project, the actual level for each result indicator should be entered in the corresponding cells once the data is collected.
Budget Narrative
The budget narrative should adequately explain the expenses set forth in the budget. Each expense line item should have a narrative explanation. Record notes about how the budget amount was calculated, the components of each line item, and other useful explanations. The narrative should align with the budget in reference so that as a reviewer reads each narrative line, the budget line corresponds. Include enough information for the budget reviewer/approver to understand budget amounts
Budget
The budget template is linked to the budget narrative template and Column A & B in the budget template will autocomplete based on the information entered in the budget narrative template. Budget category and Budget total columns will be copied automatically from the budget narrative template. In general cells that have no shading (white) require data/information to be entered. Cells that are shaded green or grey have formulas that will automatically generate data. The budget template will form the basis of reporting during the project.

## b - Logframe
Activities and Results | Indicators | Baseline Data | Targets | Data Sources | Assumptions
Impact:
Positive Psychosocial, Economic and Social transformation in the lives of BTRMU women and their children
Medium-term Outcomes:
1 Improved Psychosocial wellbeing of BTRMU women | % of women who are able to articulate their personal values and goals when asked during home visits | ? | 80% | Home follow up checklist (annual)
| % of women who demonstrate at least 4 positive social behaviours (e.g. hope, forgiveness, positive outlook, community engagement) | ? | 80% | Post rehab Evaluation meeting report (all staff)
2 Increased economic sustainability of women | % of women who stay at least six months on an income generating activity | ? | 80% | Business follow up visit annual report (checklist)
| % of women who have at least 200,000UGX on hand as back up capital after beginning their small business | ? | 70% | Savings finance report (David’s list)
3 Improved emotional and social wellbeing in the lives of BTRMU women and children | % of women who are living with their children after the rehab program | ? | 90% | Home visit (including resettlement visit)
| % of women who are reconciled back to their families | ? | 90% | One on one counseling reports (during rehab year) and Home visit (after rehab year)
| % of children that have school grades above average (50%) | ? | 80% | School Report cards
Short-term Outcomes:
1.1 Increased personal development and values education among BTRMU women | % of women who have successfully facilitated a group session demonstrating increased personal development and communication skills | ? | 80% | Group session evaluation score cards (from all staff present at session)
1.2 Increased literacy skills | % of women who score 80% in their literacy test | ? | 80% | Literacy test summary report
2.1 Improved Livelihoods skills | % of women who score 60% on their skills training exam | ? | 100% | Skills training test report
3.1 Positively transformed mindset of BTRMU women | % of women who have a positively transformed mindset (conversation filled with hope, forgiveness has occurred, have good dreams for the future, self-reliance and independence, lack of negative feelings towards her family and community – all 5 checked) | ? | 80% | One on one counseling checklist + home follow up visit checklist
3.2 Increased educational engagement and positive activities among BTRMU children | % of children who attend the holiday program that have a 100% attendance rate | ? | 70% | Attendance reports
Activities:
1.1.1 Monthly, Evening Group Sessions
1.1.2 Daily Reflective/Mindfulness Sessions | # of women who participated in daily reflective/mindfulness sessions | 0 | 15 | Attendance report
1.1.3 Structured/Group Counselling | # of women who received structured counselling | 0 | 15 | Attendance report
1.2.1 Literacy education | # of women who received literacy education | 0 | 15 | Attendance report
2.1.1 Business follow ups | # of women who received business follow up visits | 0 | 25 | business follow up report
2.1.2 Entrepreneurship training | # of women who received entrepreneurship training | 0 | 30 | Attendance report
2.1.3 Savings | # of women who have saved atleast 600,000 UGX | 0 | 15 | Savings report
3.1.1 Art Therapy | # of women who participated in art therapy | 0 | 25 | Attendance report
3.1.2 Community Network Mobilisation | # of community organisations/networks engaged | 0 | 5 | Monthly report
3.1.4 One on one counseling | # of women who were provided with one on one counseling | 0 | 15 | Counselor report
3.1.5 Resettlement of each woman | # of women who have been resettled | 0 | 15 | Counselor report
3.1.6 Health Education | # of women provided with health education | 0 | 15 | Attendance report
3.1.7 Follow up Home visits – 2 years | # of women who received home follow up visits | 0 | 20 | home follow up visit report
3.2.1 Children’s Holiday Enrichment Programme
3.2.2 School visits and Tuition support | # of children provided with tuition support | 0 | 25 | Financial quarterly report
| # of women reached out to by the drop in center | 0 | 240 | drop in center report

## d - Results Monitoring
RESULTS MONITORING TEMPLATE - Cycle 10
Result level | Result (from logframe) | Result indicator (from logframe) |  | Baseline | 10 months of rehab program | 1 year (immediately after rehab program) | 6 months year after rehab program | 2 years after rehab program (Total/Target) | Benchmark 5
|  |  |  | 2022-09-01 | 2023-06-01 | 2023-08-01 | 2024-02-01 | 2025-08-01 | date
MTO | Improved psychosocial well being | % of women who are able to articulate their personal values and goals when asked during home visits | Planned | 0 | N/A | N/A | 80% | 80%
Actual
|  | % of women who demonstrate at least 4 positive social behaviours (e.g. hope, forgiveness, positive outlook, community engagement) | Planned | 0 | N/A | 80% | N/A | N/A
Actual
MTO | Increased economic sustainability for women | % of women who stay at least six months on an income generating activity | Planned | 0 | N/A | N/A | 70% | 80%
Actual
|  | % of women who have at least 200,000UGX on hand as back up capital after beginning their small business | Planned | 0 | N/A | 70% | N/A | N/A
Actual
MTO | Improved emotional and social wellbeing in the lives of BTRMU women and children | % of women who are living with their children after the rehab program | Planned | 0 | N/A | 70% | 80% | 90%
Actual
|  | % of women who are reconciled back to their families | Planned | 0 | 50% | 70% | 90% | 90%
|  |  | Actual |  | 100%
|  | % of children that have school grades above average (50%) | Planned | 20% | 40% | 60% | 80% | 80%
|  |  | Actual |  | 50%
STO | Increased personal development and values education among BTRMU women | % of women who have successfully facilitated a group session demonstrating increased personal development and communication skills | Planned | 0 | N/A | 80% | N/A | N/A
Actual
STO | Increased literacy skill | % of women who score 80% in their literacy test | Planned | 0 | 50% | 80% | N/A | N/A
|  |  | Actual |  | 50%
STO | Improved Livelihoods skills | % of women who score 60% on their skills training exam | Planned | 0 | N/A | 100% | N/A | N/A
Actual
STO | Positively transformed mindset of BTRMU women | % of women who have a positively transformed mindset (conversation filled with hope, forgiveness has occurred, have good dreams for the future, self-reliance and independence, lack of negative feelings towards her family and community – all 5 checked) | Planned | 0 | 70% | 80% | 80% | 80%
|  |  | Actual |  | 100%
Actual
Planned
Actual
Planned
Actual
STO
MTO
Impact

## Budget
BUIKWE TOUCH REHABILITATION MINISTRIES UGANDA (BTRMU)
Project Budget –
Total Budget: $50,000 USD ¦ Exchange Rate: 3,700 UGX / USD ¦
Note: Programme staff costs are included within each programme category, as staff time is directly dedicated to delivering those services to beneficiaries. Global Giving funding covers a proportional share of the full project budget.
# | Budget Line Item | Amount (UGX) | Amount (USD) | % of Total
1. REHABILITATION & PSYCHOSOCIAL PROGRAM
1 | Rehabilitation Program Coordinator | 7418824 | 2005.09 | 4.01%
2 | Counsellor & Community Mobilisation Manager | 4472635 | 1208.82 | 2.418%
3 | Full-time Drop-in Centre Counsellor | 2680900 | 724.57 | 1.449%
4 | Matron | 2172423 | 587.14 | 1.174%
5 | Girls' Monthly Upkeep Allowance (15 women × 12 months) | 20106753 | 5434.26 | 10.87%
6 | Resettlement Support & Business Start-up Equipment | 8936335 | 2415.23 | 4.83%
7 | Medical Care – Medicines, First Aid & Health Services | 11915113 | 3220.3 | 6.441%
8 | Personal Development Books & Motivational Literature | 558521 | 150.95 | 0.3019%
9 | Food & Hygiene Items – Home Follow-up Visits | 357453 | 96.61 | 0.1932%
10 | Beds & Mattresses for Incoming Residents | 1079807 | 291.84 | 0.5837%
| SUBTOTAL – Rehabilitation & Psychosocial Program | 59698764 | 16134.8 | 32.27%
2. EDUCATION & LIVELIHOODS TRAINING
11 | Literacy Teacher | 1787267 | 483.05 | 0.9661%
12 | Vocational Skills Trainers – Contract (Hairdressing, Tailoring, Catering, Weaving) | 3261762 | 881.56 | 1.763%
13 | Training Materials – Fabric, Hair Products, Weaving Supplies, Stationery | 2736752 | 739.66 | 1.479%
14 | Entrepreneurship Workshop Refreshments | 297878 | 80.51 | 0.161%
15 | Hairdressing Practice Head Dolls | 297878 | 80.51 | 0.161%
16 | Extended Vocational Training – 6 Months Post-Program (10 women) | 5212862 | 1408.88 | 2.818%
17 | Sewing Machines (3 units) | 1005338 | 271.71 | 0.5434%
18 | Hairdressing Head Dryers (2 units) | 670225 | 181.14 | 0.3623%
19 | School Fees for Children of Participants | 8042701 | 2173.7 | 4.347%
20 | School Supplies & Books for Children | 595756 | 161.02 | 0.322%
| SUBTOTAL – Education & Livelihoods Training | 23908419 | 6461.73 | 12.92%
3. CHILDREN & FAMILY WELFARE
21 | Housekeeping & Children Welfare Officer | 2172423 | 587.14 | 1.174%
22 | Cook | 1629317 | 440.36 | 0.8807%
23 | Children's Toys & Play Materials | 111704 | 30.19 | 0.06038%
| SUBTOTAL – Children & Family Welfare | 3913444 | 1057.69 | 2.115%
4. COMMUNITY OUTREACH & PREVENTION
24 | Business Mobiliser | 2715529 | 733.93 | 1.468%
25 | Project Coordinator | 2498286 | 675.21 | 1.35%
26 | Prevention Program Materials (reusable pads & liquid soap training) | 446817 | 120.76 | 0.2415%
27 | Community Mobilisation Meeting Refreshments | 74469 | 20.13 | 0.04025%
| SUBTOTAL – Community Outreach & Prevention | 5735101 | 1550.03 | 3.1%
5. DROP-IN CENTRE PROGRAM
28 | Security Guard | 1629317 | 440.36 | 0.8807%
29 | Drop-in Centre Office Rent (12 months) | 2234084 | 603.81 | 1.208%
30 | Participant Allowances – 10 Women × 3 Months | 2234084 | 603.81 | 1.208%
| SUBTOTAL – Drop-in Centre Program | 6097485 | 1647.97 | 3.296%
6. OPERATIONS & PROGRAMME SUPPORT
31 | Executive Director | 10862115 | 2935.71 | 5.871%
32 | Programme Administrator | 5431057 | 1467.85 | 2.936%
33 | Secretary / Cashier | 4887952 | 1321.07 | 2.642%
34 | Accountant | 5431057 | 1467.85 | 2.936%
35 | Cleaner | 1916844 | 518.07 | 1.036%
36 | Statutory Payroll Contributions – NSSF (15%) | 7515770 | 2031.29 | 4.063%
37 | Daily Meals – Food Supplies & Charcoal for Women & Staff | 28946799 | 7823.46 | 15.65%
38 | Office & Halfway House Rent (12 months) | 6255434 | 1690.66 | 3.381%
39 | Electricity (12 months) | 1340450 | 362.28 | 0.7246%
40 | Water & Sewer (12 months) | 1787267 | 483.05 | 0.9661%
41 | Transport – Business Visits, Home Visits, Health Centres, School Fees | 2755370 | 744.69 | 1.489%
42 | Transport – Purchases & Supplies Delivery | 316495 | 85.54 | 0.1711%
43 | Printing, Photocopying & Office Stationery | 484051 | 130.82 | 0.2616%
44 | Office Books & Supplies | 335113 | 90.57 | 0.1811%
45 | Equipment Maintenance & Repair | 1098424 | 296.87 | 0.5937%
46 | Property & Grounds Supplies | 1340450 | 362.28 | 0.7246%
47 | Groundskeeping Services | 446817 | 120.76 | 0.2415%
48 | Audit & Professional Fees | 819164 | 221.4 | 0.4428%
49 | Legal Services | 297878 | 80.51 | 0.161%
50 | Airtime & Wireless Communications | 1191511 | 322.03 | 0.6441%
51 | Internet Access | 446817 | 120.76 | 0.2415%
52 | Food – Medical Care Fluids (health centre visits) | 1442073 | 389.75 | 0.7795%
53 | Bank Charges | 297878 | 80.51 | 0.161%
| SUBTOTAL – Operations & Programme Support | 85646786 | 23147.78 | 46.3%
| GRAND TOTAL | 184999999 | 50000 | 100%
BUDGET SUMMARY BY PROGRAMME AREA
Programme Area |  | UGX | USD | % Share
1. Rehabilitation & Psychosocial Program |  | 59698764 | 16134.8 | 32.27%
2. Education & Livelihoods Training |  | 23908419 | 6461.73 | 12.92%
3. Children & Family Welfare |  | 3913444 | 1057.69 | 2.115%
4. Community Outreach & Prevention |  | 5735101 | 1550.03 | 3.1%
5. Drop-in Centre Program |  | 6097485 | 1647.97 | 3.296%
6. Operations & Programme Support |  | 85646786 | 23147.78 | 46.3%
TOTAL |  | 184999999 | 50000 | 100%

## g - Activity Monitoring (hidden)
ACTIVITY MONITORING TEMPLATE | [28 empty] | OPTIONAL
| Activity indicator | UOM |  | Month | [11 empty] | Total Target | Average monthly target | Comment on difference between planned and actual | Total target # of beneficiaries |  |  | Beneficiaries reached THIS month |  |  | Total beneficiaries reached TO DATE |  |  | Total # of indirect beneficiaries TO DATE
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 |  |  |  | M | F | Total | M | F | Total | M | F | Total | M | F | Total
a | #REF! | #REF! | Planned | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  | 0 | 15 | 15 | 0 | 0 | 0 | 499 | 301 | 800 |  |  | 0
|  |  | Actual |  | 500 | 900 | 700 | 800 | 1100 | 600 | 1000 | 700 | 800 |  |  | 7100 | 788.8889
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
b | #REF! | #REF! | Planned | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  | 0 | 15 | 15 | 0 | 0 | 0 | 1800 | 2200 | 4000 |  |  | 0
|  |  | Actual | Month 3: 800 | 800 | 800
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
1 | # of women who received literacy education | women | Planned | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 0 | 0 | 0 | 15 | 15 |  | 0 | 35 | 35 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
2 | # of women who received business follow up visits (3 previous rehab cycles) | women | Planned | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 |  | 0 | 15 | 15 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
3 | "# of women (current rehabilitation cycle) who received livelihood skills & entrepreneurship training | women | Planned | 0 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 35 | 35 | 35 | 35 | 45 | 22.2727 |  | 0 | 180 | 180 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Actual | [12 empty] | 0 | 0
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
4 | # of women who have saved atleast 600,000 UGX | women | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  | 0 | 6 | 6 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Actual | [12 empty] | 0 | 0
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
5 | # of women who participated in art therapy | women | Planned | 25 | 20 | 20 |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 25 | 25 |  | 0 | 15 | 15 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
6 | # of community organisations/networks engaged | community organisations/networks | Planned | 0 | 0 | 0 | 1 | 0 | 2 | 0 | 0 | 0 | 3 | 0 | 0 | 6 | 2 |  | 0 | 15 | 15 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Actual | [12 empty] | 0 | 0
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
7 | # of women (2021 rehab cycle) provided with livelihoods skills advancement training | women | Planned | 0 | 10 | 10 | 10 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 10 | 10 |  | 0 | 10 | 10 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
8 | #of women who completed the rehabilitation program and have been resettled | women | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 15 | 15 |  | 0 | 15 | 15 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Actual | [12 empty] | 0 | 0
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
9 | #REF! | #REF! | C | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  | 0 | 180 | 180 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Actual | [12 empty] | 0 | 0
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
10 | # of women who received psychosocial support and counselling through the drop in center | women | Planned | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 0 | 20 | 20 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
11 | #REF! |  | Planned | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | 0 |  | 10 | 15 | 25 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Actual | [12 empty] | 0 | 0
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
12 | # of women (previous rehab cycles) who received home follow up visits and psychosocial support | women | Planned | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 |  | 0 | 180 | 180 |  |  | 0 |  |  | 0 |  |  | 0
|  |  | Actual | [12 empty] | 0 | 0
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
13 | # of children provided with tuition support | children | Planned | 25 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 75 | 25 |  | 450 | 450 | 900 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
14 | # of women who received drop in center services - including health education and services | girls | Planned | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 240 | 20 |  | 60 | 60 | 120 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
15 | # of girls and boys reached with prostitution prevention education | individuals | Planned | 10 | 0 | 300 | 0 | 0 | 0 | 300 | 0 | 0 | 0 | 300 | 0 | 910 | 227.5 |  | 450 | 630 | 1080 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
16 | # of men and women (including mothers) reached with prostitution prevention education | individuals | Planned | 20 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 130 | 10.8333 |  | 450 | 450 | 900 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
|  |  | Planned | [15 empty] | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
18 | # of women who participated in daily reflective/mindfulness sessions |  | Planned | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 |  | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0
Actual
|  |  | % to-date achievement | [12 empty] | 0% | 0% | bar: Month 1 to Month 12
19 | # of women who attended structed counseling | women | Planned | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 100%
Actual
|  |  | % to-date achievement | Month 1: 100%; Month 2: 100%; Month 3: 100%; Month 4: 100%; Month 5: 100%; Month 6: 100%

## c - Activity Planning
ACTIVITY PLANNING TEMPLATE
| Activity indicator | UOM | Month | [11 empty] | Total target | Average monthly target | Targeted # of direct beneficiaries |  |  | Responsible officer | Explanation of beneficiary numbers
|  |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug |  |  | Male | Female | Total
1 | # of women who received psychosocial support and counselling through the rehabilitation program | women | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15
2 | # of women who received literacy education | women | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 |  |  |  |  | 15 | 15 | 0 | 15 | 15
3 | # of women who received business follow up visits (3 previous rehab cycles) | women | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 30 | 0 | 30
4 | "# of women (current rehabilitation cycle) who received livelihood skills & entrepreneurship training | women |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 35 | 35 | 35 | 35 | 35 | 22.2727 | 0 | 35 | 35
5 | # of women who have saved atleast 600,000 UGX | women | Month Aug: 15 | 15 | 15 | 0 | 15 | 15
6 | # of women who participated in art therapy | women | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 180 | 20 | 0 | 180 | 180
7 | # of community organisations/networks engaged | community organisations/networks | Month Dec: 1; Month Feb: 2; Month Jun: 3 | 6 | 2 |  | 6 | 6
8 | # of women attending/receiving values and life-skills education | women | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 0 | 15 | 15
9 | # of women (current rehab cycle) provided with livelihood inputs/assets | women | Month Aug: 15 | 15 | 15 |  | 15 | 15
10 | # of women (2021 rehab cycle) provided with livelihoods skills advancement training | women | Month Oct: 10; Month Nov: 10; Month Dec: 10; Month Jan: 10; Month Feb: 10; Month Mar: 10 | 10 | 10 | 0 | 10 | 10
11 | #of women who completed the rehabilitation program and have been resettled | women | Month Aug: 15 | 15 | 15 | 0 | 15 | 15
12 | # of women who received psychosocial support and counselling through the drop in center | women | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 180 | 180
13 | # of women (previous rehab cycles) who received home follow up visits and psychosocial support | women | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 0 | 20 | 20
14 | # of children provided with tuition support | children | Month Sep: 25; Month Feb: 25; Month Jun: 25 | 25 | 25 | 10 | 15 | 25
15 | # of women who received drop in center services - including health education and services | women | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 180 | 20 | 0 | 180 | 180
16 | # of girls and boys reached with prostitution prevention education | individuals | Month Nov: 300; Month Mar: 300; Month Jul: 300 | 900 | 300 | 450 | 450 | 900
17 | # of men and women (including mothers) reached with prostitution prevention education | individuals | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 120 | 10 | 60 | 60 | 120
18 | # of people reached with prostitution and trafficking awareness education | women | 20 | 20 | 320 | 20 | 20 | 20 | 320 | 20 | 20 | 20 | 320 | 20 | 1080 | 95 | 450 | 630 | 1080
19 | # of people provided with trafficking awareness and prevention education | people | Month Nov: 300; Month Mar: 300; Month Jul: 300 | 900 | 300 | 450 | 450 | 900
0
0
[21 empty] | F | M
[20 empty] | psychosocial supp. | 215 | 0
[20 empty] | educational assist. | 15 | 10
[20 empty] | traff. Aware | 450 | 450
[17 empty] | 520 | 740