PROJECT ON ACCESS TO JUSTICE FOR WOMEN IN NORTH KIVU PROVINCE

1. Project Title

Strengthening Access to Justice and Protection of Women’s Rights in North Kivu Province

2. Project Intervention Area

North Kivu Province, Democratic Republic of Congo

Targeted cities and territories:

- Goma

- Beni

- Butembo

- Lubero

3. Project Duration

Duration: 12 months

Implementation period: January–December (or depending on the project start date and funding availability).

4. Background and Justification

North Kivu Province continues to face prolonged insecurity, armed conflict, population displacement, gender-based violence (GBV), and institutional fragility that limit access to social and judicial services. Women and girls remain among the groups most exposed to violations of their fundamental rights.

In the targeted areas of Goma, Beni, Butembo, and Lubero, women face several barriers to accessing justice, including:

- Limited knowledge of their legal rights;

- High legal and judicial costs;

- Long distances to judicial institutions and services;

- Social stigma against survivors and victims;

- Insufficient legal assistance services;

- Weak community-based protection mechanisms.

This project aims to strengthen women’s access to justice through awareness raising, legal assistance, and capacity building of community actors.

5. Overall Objective

To contribute to improving equitable access to justice and the protection of women’s fundamental rights in North Kivu Province.

6. Specific Objectives

- Increase women’s awareness of their rights and justice mechanisms.

- Facilitate access to legal aid services for vulnerable women.

- Strengthen the capacity of community actors regarding women’s rights protection.

- Develop community mechanisms for prevention and referral of rights violations.

7. Expected Results

Result 1

Women have improved knowledge of their rights and judicial procedures.

Indicators:

- Number of women sensitized;

- Number of awareness campaigns conducted;

- Percentage of participants with improved knowledge.

Result 2

Vulnerable women access legal aid services.

Indicators:

- Number of women receiving legal assistance;

- Number of cases supported;

- Number of resolved or referred cases.

Result 3

Community actors have strengthened capacities.

Indicators:

- Number of actors trained;

- Number of community actions implemented.

8. Main Activities

Community Awareness Activities

- Conduct community awareness sessions on women’s rights;

- Broadcast local radio programs;

- Produce and distribute awareness materials.

Legal Assistance Activities

- Establish mobile legal clinics;

- Provide free legal assistance to vulnerable women;

- Refer victims to competent service providers.

Capacity Building Activities

- Train community leaders;

- Train community paralegals;

- Organize workshops on women’s rights and gender-based violence.

Community Protection Activities

- Establish community referral mechanisms;

- Organize community dialogues with local authorities and stakeholders.

9. Beneficiaries

Direct Beneficiaries

- Women survivors of violence;

- Displaced women;

- Widows;

- Vulnerable girls and young women.

Estimated number: 3,000 direct beneficiaries

Indirect Beneficiaries

- Families;

- Community leaders;

- Community members.

Estimated number: 15,000 indirect beneficiaries

10. Implementation Schedule

| Activities | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Staff recruitment and inception meeting | X | X |  |  |  |  |  |  |  |  |  |  |
| Baseline assessment | X | X |  |  |  |  |  |  |  |  |  |  |
| Development and production of awareness materials |  | X | X |  |  |  |  |  |  |  |  |  |
| Community awareness campaigns |  |  | X | X | X | X | X | X | X | X | X |  |
| Radio programs on women’s rights |  |  | X | X | X | X | X | X | X | X | X | X |
| Establishment of mobile legal clinics |  |  | X | X | X | X | X | X | X | X |  |  |
| Free legal assistance and case referrals |  |  | X | X | X | X | X | X | X | X | X | X |
| Training of community leaders and paralegals |  |  | X | X |  |  | X | X |  |  |  |  |
| Community dialogues with local authorities |  |  |  | X | X |  |  | X | X |  |  |  |
| Field monitoring missions |  |  | X |  | X |  | X |  | X |  | X |  |
| Mid-term evaluation |  |  |  |  |  | X |  |  |  |  |  |  |
| Final evaluation and final report |  |  |  |  |  |  |  |  |  |  | X | X |

11. Detailed Budget (USD)

| Budget Line | Description | Quantity | Unit Cost (USD) | Total (USD) |
| --- | --- | --- | --- | --- |
| 1. Community Awareness |  |  |  |  |
| Community awareness meetings | 24 | 150 | 3,600 |  |
| Production of materials (posters, brochures, leaflets) | 1 lot | 1,500 | 1,500 |  |
| Local radio broadcasts | 12 | 150 | 1,800 |  |
| Transport and logistics | 1 lot | 1,100 | 1,100 |  |
| Subtotal |  |  |  | 8,000 |
| 2. Legal Assistance and Mobile Clinics |  |  |  |  |
| Mobile legal clinic activities | 12 | 500 | 6,000 |  |
| Legal support for vulnerable cases | 50 | 100 | 5,000 |  |
| Referral and accompaniment services | 1 lot | 2,000 | 2,000 |  |
| Case documentation and management | 1 lot | 2,000 | 2,000 |  |
| Subtotal |  |  |  | 15,000 |
| 3. Capacity Building |  |  |  |  |
| Training for community leaders | 2 | 1,500 | 3,000 |  |
| Training for community paralegals | 2 | 1,500 | 3,000 |  |
| Training materials and documentation | 1 lot | 2,000 | 2,000 |  |
| Subtotal |  |  |  | 8,000 |
| 4. Community Protection Activities |  |  |  |  |
| Community dialogues | 8 | 400 | 3,200 |  |
| Establishment of community mechanisms | 4 | 700 | 2,800 |  |
| Subtotal |  |  |  | 6,000 |
| 5. Monitoring and Evaluation |  |  |  |  |
| Field monitoring missions | 5 | 500 | 2,500 |  |
| Mid-term evaluation | 1 | 1,000 | 1,000 |  |
| Final evaluation | 1 | 1,500 | 1,500 |  |
| Subtotal |  |  |  | 5,000 |
| 6. Administration and Operations |  |  |  |  |
| Communication and internet | 12 | 150 | 1,800 |  |
| Office supplies | 12 | 100 | 1,200 |  |
| Local transport and coordination | 12 | 250 | 3,000 |  |
| Administrative expenses | 1 lot | 2,000 | 2,000 |  |
| Subtotal |  |  |  | 8,000 |

Total Budget Summary

| Category | Amount (USD) |
| --- | --- |
| Community Awareness | 8,000 |
| Legal Assistance and Mobile Clinics | 15,000 |
| Capacity Building | 8,000 |
| Community Protection Activities | 6,000 |
| Monitoring and Evaluation | 5,000 |
| Administration and Operations | 8,000 |
| Grand Total | 50,000 USD |

- Project Impact:

The project will contribute to improving women’s access to fair justice in conflict-affected areas of Eastern DR Congo. It will strengthen their knowledge of their rights, reduce economic barriers limiting their access to justice services, and increase their participation in justice and governance mechanisms. The project will also help reduce violence, discrimination, and impunity while promoting sustainable peace, gender equality, and community development.

13. Conclusion

This project will contribute to strengthening women’s access to justice mechanisms in Goma, Beni, Butembo, and Lubero. It will improve legal awareness, access to legal assistance, and community participation in the protection of women’s rights while considering the local context and available resources within a USD 50,000 budget framework.