## Project schedule
| Enhanced Vaccines for Sickle Cell Kids | [5 empty] | Project start: | [7 empty] | 2026-09-01
| Jackson Ameh | Project Lead |  |  |  |  | Display week: | [7 empty] | 4
[7 empty] | 2026-09-21 | [6 empty] | 2026-09-28 | [6 empty] | 2026-10-05 | [6 empty] | 2026-10-12 | [6 empty] | 2026-10-19 | [6 empty] | 2026-10-26 | [6 empty] | 2026-11-02 | [6 empty] | 2026-11-09
| TASK | ASSIGNED TO | PROGRESS | START | END | time axis 2026-09-21 to 2026-11-15
 | time axis 2026-09-21 to 2026-11-15
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the current day within the project schedule.
Initiation
| State Ministry of Health Engagement | Project Lead | 0% | 2026-09-01 | 2026-09-04 | 4
| Hospital Leadership Meetings | Project Lead | 0% | 2026-09-04 | 2026-09-14 | 11
| Formalize partnerships with 3 laboratories for genotype testing | Project Lead | 0% | 2026-09-14 | 2026-09-19 | 6
| Vaccine Supply Coordination | Project Lead | 0% | 2026-09-19 | 2026-09-22 | 4
| Document Sample Logistics Protocol | Project Lead | 0% | 2026-09-23 | 2026-09-27
| Recruit 3 Community Health Workers (CHWs) across the three LGAs. | Project Lead | 0% | 2026-09-28 | 2026-10-04
| CHW Training | Project Lead | 0% | 2026-10-07 | 2026-10-08
| Develop Records Management System | IT Officer | 0% | 2026-09-01 | 2026-10-31
Phase 2 - Execution
| Integrate genotype testing into facility births @ appropirate age | Project Lead | 0% | 2026-10-09 | 2027-04-07 | 181
| Lab Testing & 72‑Hour Reporting | Project Lead | 0% | 2026-10-10 | 2027-07-07 | 271
| Integrate Vaccination into Clinic Days | Project Lead | 0% | 2026-10-10 | 2026-12-09 | 61
| Vaccine Transport & Cold Chain | Project Lead | 0% | 2026-09-20 | 2026-09-26
| Monthly Radio Talk Show | Project Lead | 0% | 2026-09-15 | 2027-06-12
| Monthly Antenatal Clinic Talks | Project Lead | 0% | 2026-10-10 | 2027-07-07 | 271
Monitoring and Evaluation
| Data Collection | Data Analyst | 1% | 2026-09-19 | 2027-06-16 | 271
| Monthly Reporting | Data Analyst | 0% | 2026-09-20 | 2027-06-17 | 271
| Mid-year progress report | Data Analyst | 0% | 2026-09-19 | 2027-03-18 | 181
| Endline Evaluation | Data Analyst | 0% | 2027-08-07 | 2027-08-22 | 16
Evaluation
| Monitor progress | Gokce Aslan | 25% | 2026-09-21 | 2026-09-24 | 4
| Track expenses | Hayden Cook | 25% | 2026-09-24 | 2026-09-28 | 5
| Evaluate progress | Jens Martensson | 50% | 2026-09-29 | 2026-10-02 | 4
| Address risks | Nuria Acevedo | 60% | 2026-09-26 | 2026-09-29 | 4
| Gather feedback | Olivia Wilson | 50% | 2026-09-28 | 2026-10-03 | 6
Formulas:
Display week: = [Display week:, row below]

## Project Schedule2
Phase | Category | Task | Description | Assigned To | Start Date | End Date
Phase 1 - Initiation | Stakeholder Engagement | State Ministry of Health Engagement | Formal introductory meeting; align on project goals
|  | Hospital Leadership Meetings | Meet Heads of Sickle Cell Clinics at Keffi, Karu, and Toto General Hospitals.
|  | Formalize partnerships with 3 laboratories for genotype testing | Formalize collaboration with 3 accredited labs for genotype testing; define turnaround time (72 hours), sample handling, and reporting
|  | Vaccine Supply Coordination | Work with hospital pharmacists to lead procurement
|  | Document Sample Logistics Protocol | Define chain‑of‑custody from collection → transport → lab → result reporting; include legal compliance and biosafety.
| Recruitment & Training | Recruit 3 Community Health Workers (CHWs) across the three LGAs.
|  | CHW Training | SCD basics, newborn screening, vaccine schedules, community sensitization, and follow‑up procedures.
| Records Management System | Develop Records Management System | Build a digital system to record and track the datapoints in sheet2
Develop System Audit protocol
Phase 2 - Service Delivery | Newborn Genotype Screening | Integrate genotype testing into facility births | Ensure every newborn delivered at the three hospitals is screened.
|  | Lab Testing & 72‑Hour Reporting | Labs process samples and sends result to the hospital. Hospital provides copies to Desk Officer on weekly basis
| Enhanced Vaccination for SCD Infants | Integrate Vaccination into Clinic Days | Administer PCV13, PPSV23, and meningococcal vaccines during Sickle Cell Clinic Days.
|  | Vaccine Transport & Cold Chain | Define how vaccines move from Abuja suppliers → hospital pharmacies → clinic days.
| Community Awareness & Outreach | Monthly Radio Talk Show | CHWs + clinicians discuss early testing and enhanced vaccines, Stigmatization, benefits of genotype testing, caring for SCD patients, etc
|  | Monthly Antenatal Clinic Talks | Educate pregnant women on newborn screening and SCD risks.
Phase 3 - M & E | Monitoring, Evaluation & Reporting | Data Collection | CHWs and facility staff provide screening, vaccination, and outreach data to Desk Officer who then enters it into the Records Management System.
|  | Monthly Reporting | Case Officer generates monthly reports exportable in excel and PDF
|  | Mid-year progress report | Review performance, and adjust outreach strategy
|  | Endline Evaluation | Measure outcomes, produce final donor report.