## Project Title

Classrooms for Out-of-School Children in Northeast Nigeria

## Project Summary (500 characters)

Nigeria has one of the world's largest populations of out-of-school children due to poverty, insecurity, and inadequate educational infrastructure. This project will construct and equip six child-friendly classrooms, including sanitation facilities and learning materials, to provide quality education for 600 out-of-school children aged 6–14 in Northeast Nigeria over 24 months through community participation and government partnerships.

# PROJECT STORY

In Northeast Nigeria, thousands of children remain excluded from education due to poverty, conflict, displacement, inadequate infrastructure, and limited access to safe learning environments. Many communities lack sufficient classrooms, forcing children to travel long distances or abandon education entirely. Girls face additional barriers due to inadequate sanitation facilities and social vulnerabilities, while many boys become engaged in child labor.

Education is one of the most powerful tools for breaking the cycle of poverty and vulnerability. However, in many rural communities, overcrowded classrooms, poor infrastructure, and a shortage of educational resources continue to prevent children from accessing quality education.

This project seeks to build and equip six safe, inclusive, and child-friendly classrooms in underserved communities in Northeast Nigeria. The intervention will provide educational opportunities for approximately 600 out-of-school children aged 6–14 years while strengthening community ownership, improving educational outcomes, and contributing to long-term social and economic development.

# THE PROBLEM

Nigeria has the world's highest number of out-of-school children, estimated at between 18.3 and 20 million children. The burden is particularly severe in the Northeast region, where poverty, insecurity, displacement, inadequate infrastructure, and social exclusion limit educational opportunities.

In the target communities:

- Existing schools are overcrowded and unable to accommodate additional learners.

- Many children walk long distances to access educational facilities.

- Schools lack adequate classrooms, furniture, and learning materials.

- Girls face barriers due to inadequate sanitation facilities.

- Poverty contributes to child labor, early marriage, and school dropout.

- Vulnerable and displaced children remain excluded from formal education.

Without intervention, these children face increased risks of illiteracy, unemployment, exploitation, poverty, and social exclusion.

# THE SOLUTION

This project will construct and fully equip six child-friendly classrooms to provide safe, inclusive, and quality educational opportunities for 600 out-of-school children in Northeast Nigeria.

The project will include:

- Construction of six standard classrooms.

- Construction of an administrative office.

- Installation of gender-sensitive sanitation facilities.

- Provision of safe water supply and handwashing stations.

- Installation of solar-powered lighting systems.

- Provision of desks, chairs, and educational equipment.

- Distribution of textbooks and learning materials.

- Training of teachers in inclusive education and child protection.

- Community mobilization and school enrollment campaigns.

- Establishment of School Management Committees.

The project will be implemented over a 24-month period through strong partnerships with communities, local education authorities, and other stakeholders.

# PROJECT ACTIVITIES

### Activity 1: Community Assessment and Mobilization

- Conduct baseline assessments.

- Identify target communities and beneficiaries.

- Engage traditional leaders and stakeholders.

- Establish School Management Committees.

- Conduct community awareness campaigns.

### Activity 2: Construction of Educational Facilities

- Prepare construction sites.

- Construct six classrooms.

- Construct one administrative office.

- Build gender-sensitive sanitation facilities.

- Install water supply systems.

- Construct school fencing and security facilities.

- Install solar energy systems.

### Activity 3: Provision of Educational Equipment

- Procure classroom furniture.

- Provide teacher furniture.

- Install whiteboards and teaching aids.

- Procure textbooks and learning materials.

- Establish starter library resources.

### Activity 4: Teacher Capacity Development

- Recruit teachers.

- Conduct teacher orientation.

- Deliver child protection training.

- Conduct inclusive education training.

- Strengthen classroom management skills.

### Activity 5: Enrollment and Community Engagement

- Conduct enrollment campaigns.

- Organize parent engagement meetings.

- Conduct house-to-house sensitization.

- Promote girls' education and inclusion.

### Activity 6: Monitoring, Evaluation, and Learning

- Conduct baseline survey.

- Undertake routine monitoring visits.

- Conduct mid-term evaluation.

- Conduct final evaluation.

- Document lessons learned and best practices.

# EXPECTED OUTPUTS

By the end of the project:

- Six classrooms constructed and operational.

- One administrative office established.

- Water and sanitation facilities installed.

- 600 out-of-school children enrolled.

- 20 teachers trained.

- Six School Management Committees established.

- School attendance increased to at least 80%.

- School retention increased to at least 85%.

# POTENTIAL LONG-TERM IMPACT

This project will create lasting educational opportunities for 600 out-of-school children by providing safe, inclusive, and well-equipped learning environments. Increased access to education will improve literacy, school retention, and future employment opportunities while reducing child labor and early marriage. Community ownership, teacher development, and government partnerships will ensure sustainable educational outcomes and contribute to long-term socioeconomic development in Northeast Nigeria.

# SUSTAINABILITY PLAN

The project sustainability strategy includes:

### Community Ownership

School Management Committees will oversee school maintenance, management, and community participation.

### Government Partnership

The project will collaborate closely with local and state education authorities to ensure teacher deployment and institutional support.

### Capacity Building

Teachers, school administrators, and community leaders will receive ongoing training in educational management and maintenance.

### Maintenance Fund

Communities will establish school maintenance funds to support repairs and upkeep.

### Long-Term Partnerships

Partnerships with local governments, private sector organizations, and international donors will support future expansion.

# MONITORING AND EVALUATION

| Indicator | Baseline | Target |
| --- | --- | --- |
| Classrooms constructed | 0 | 6 |
| Children enrolled | 0 | 600 |
| Attendance rate | 30% | 80% |
| Retention rate | 40% | 85% |
| Teachers trained | 0 | 20 |
| Community campaigns conducted | 0 | 10 |
| School Management Committees established | 0 | 6 |

Monitoring tools will include:

- Baseline and end-line surveys

- Enrollment records

- Attendance registers

- Classroom observations

- Monthly monitoring visits

- Community feedback mechanisms

- Mid-term and final evaluations

# DETAILED PROJECT BUDGET (USD)

| Budget Item | Amount (USD) |
| --- | --- |
| Site preparation and land clearing | 8,000 |
| Construction of six classrooms | 90,000 |
| Administrative office | 8,000 |
| Gender-sensitive sanitation facilities | 12,000 |
| Borehole and water supply system | 10,000 |
| Handwashing stations | 3,000 |
| School fencing and security gate | 12,000 |
| Solar lighting installation | 6,000 |
| Student desks and chairs | 30,000 |
| Teacher furniture | 3,000 |
| Whiteboards | 1,500 |
| Office furniture | 2,500 |
| Computers and printer | 3,000 |
| Textbooks | 12,000 |
| Student supplies and stationery | 9,000 |
| Teaching aids | 4,000 |
| Library starter kits | 5,000 |
| Teacher training workshops | 6,000 |
| School Management Committee training | 2,000 |
| Community mobilization campaigns | 5,000 |
| Enrollment drives | 2,000 |
| Baseline assessment | 3,000 |
| Mid-term evaluation | 3,000 |
| Final evaluation | 4,000 |
| Monitoring visits | 6,000 |
| Project Coordinator | 14,400 |
| Project Officer | 9,600 |
| Finance/Admin Officer | 9,600 |
| Office operations | 6,000 |
| Transportation and logistics | 6,000 |
| Contingency | 12,400 |
| TOTAL PROJECT COST | USD 308,000 |

## Funding Goal

USD 308,000

## Project Duration

24 Months

## Direct Beneficiaries

- 600 out-of-school children

- 20 teachers

- 300 parents and caregivers

## Indirect Beneficiaries

- Local communities

- Educational authorities

- Future generations of school-age children