- Budget form

- Sanitary pads production and training funds requested from Global Giving

| Budget line | Qty | Rate UGX | Period | In UGX | In $ |
| --- | --- | --- | --- | --- | --- |
| People and time (salaries) |  |  |  |  |  |
| Project coordinator | 1 | 250,020/ | 1 x 250,020/x 12 months | 3,000,250/ | 1091 |
| Field officers | 2 | 250,020/ | 2 x 250,020/ x12 months | 6,000,480/ | 2181.9 |
| Instructors | 4 | 180,000/ | 4 x18,000/ x 12months | 8,640,000/ | 3141.8 |
| Accountant /Bursar | 1 | 250,020/ | 1 x250,020/ x 12months | 3,000,250/ | 1091 |
| Office and administration |  |  |  |  |  |
| Administrative Cost | 1 | 2,604,250/ | 12moths | 2,604,250/ | 947 |
| Other (please specify) Program Costs |  |  |  |  |  |
| IEC Materials (2,000 copies) |  | 1,000/ | 2000/ x1000/ x1 | 2,000,000/ | 727 |
| Radio Program |  | 1,000,000/ | 1,000,000/ x 3moths | 3,000,000/ | 1090.9 |
| TV talk shows | 3 | 1,666,333/ | 1,666,333/ x 3months | 4,998,999/ | 1817.8 |
| Materials: |  |  |  |  |  |
| Garment | 45pc | 180,000/ | 1,80000/ x45 x 1 | 8,100,000/ | 2945.4 |
| Cotton rolls | 120 | 10,000/ | 1,0000/ x120 x 1 | 1,200,000/ | 436 |
| Polythene (90meter) | 90 | 8,000/ | 8,000/ x 90 x 1 | 720,000/ | 261.8 |
| Threads ( 90 packets) | 90pc | 2,835/ | 2,832/ x 45x 1 | 127,462/ | 46.3 |
| Sewing machines maintenance | 1 |  | 127462/ x1 | 127,462/ | 46.3 |
| Head teachers Training workshop (40H/T) | 2days | 2,362,525/ | 2 x 40pp x2362525 x1 | 4,725,050/ | 1718.2 |
| Communication and networking |  | 1,595,000/ | 1595000/ x 1 | 159,500/ | 580 |
| Board Meetings | 12 | 70,000/ | 70000/ x12 x 1 | 840,000/ | 305.4 |
| General Assembly | 1 | 128,850/ | 1,288,500/ x1 | 1,288,500/ | 468.5 |
| Monitoring and Evaluation | 12 | 190,625/ | 190,625/ x12 x 1 | 2,287,500/ | 831.8 |
| Audit | 1 | 600,000/ | 600000/ x1 | 600,000/ | 218.1 |
| TOTALS |  |  |  |  | 20,000.2 |

- The project coordinator of the program will be given an allowance of 1091 yearly, this means that would be paid 90.91$ monthly.

- We shall have two field officers who will be following up the program and they will be paid 90.91$ each and every month and this totals to 2181.9 $ a year.

- The program will have 4tecnician instructors who will be training the students in schools and also producing reusable sanitary pads throughout the year and they will be paid 65.4$ a month this means that they will be paid 3181.8$ a year.

- The accountant will be working on regulating and guiding in programs funds and will be paid 90.91 $ a month and 1091$ a year.

- Administrative cost will help in running the office daily work throughout the program and it is 947$

- Information communication Education materials will help in creating awareness about the whole program at is allocated for 727$

- Our field officers will be holding radio talk shows people to know what Poor Urban Girl Child Sanitary pad production program is all about and the funds allocated to it is 490.9$

- Funds for materials needed to produce reusable sanitary pads for distribution is 3736$

- Funds for communication and networking is 580$ and will be helping us in regards to reaching out to other development organizations and strengthening UYSTO relationship within Uganda and Outside Uganda organization involved in the similar projects.

- Head teachers training, this will embrace the program as head teachers will be part of it and  funds for their involvement is 1718.2 $

- UYSTO board meetings are held every month and this will help planning and development of the project and funds allocated is 305.4$.

- General Assembly meetings are held once in year and this reviews all the activities and projects done and approves them for further other projects operation and the funds allocated for it in this project is 468.5$

- Motoring and Evaluation is done to see the progress of the project and this is throughout done. It’s funds is 831.8$.

- Audits reports are done every the end of the project and this fund 218.1$ allocated to this item, will be used in carrying auditing.

The whole program will take 20000.2$