## Slide 1
Friendship Charity Association
Tibetan Crafts Preservation
June 2011

## Slide 2: Project Objective and Process
  Assess current operations and process: identify current objectives, key stakeholders, current structure, current fundraising avenues, etc.
  Identify key requirements: volunteer resources, capital resources, materials, design experts for new designs etc
  Assess/develop an organization structure with detailed responsibilities
  Evaluate fundraising and self-funding opportunities
  Defined objectives for Tibetan Crafts project
  Clear organizational structure
  Sustainable fundraising process
  Roadmap for implementation
  Develop a self-sustaining model to support traditional Tibetan Crafts
  Provide strategy and guidance to enable Friendship Charity to develop a more formalized structure and process for its project
Objective
Pivot Support Areas
Deliverables

## Slide 3
Phase 1:
June
Phase 2:
June/July
Phase 3:
July/August
Proposed Timeline
Funding
Strategy
Targeted Donor Strategy
Define Process and Organization Structure
Assess Current Operations
  Determine current objectives for Tibetan Crafts preservation
  Determine the current organizational structure and fundraising process
  Identify key stakeholders involved with the preservation project
  Define mission and objective for Tibetan Crafts Preservation project
  Develop organization structure with detailed responsibilities
  Identify necessary volunteer resources, capital, and materials
  Develop strategies to expand the Tibetan Crafts project in local villages
  Identify funding requirements for the project
  Define fundraising sources to meet funding requirements (donors, companies, grants, sales of crafts, etc.)
  Develop targeted fundraising strategies for each funding source
Key Project Steps
3 Weeks
3 Weeks
1-2 weeks
Develop Roadmap
Phase 3:
August
  Summarize recommendations from previous phases
  Develop a roadmap and workplan for Friendship Charity Association to implement recommendations
  Identify milestones to track progress
1-2 Weeks

## Slide 4
  Review project objectives, scope, and timeline
  Discuss revisions to proposal and project scope
Next Steps