COMMUNITY BASED FIRST AID PROJECT

FI

- Contact Information of PV.

| Name of your organization: | Progressive Volunteers |
| --- | --- |
| Name of suggested project manager: | Jeremiah Mzee |
| Age of project manager (between 18-35): | 30 |
| Sex of project manager (male / female): | Male |
| His/her current position: | Executive Director |
| Phone: | +254 721774820 |
| E-mail: | jeremiah@progressivevolunteers.or.ke |
| Postal Address: | P.O BOX 21579-00500 |
| Physical Address/Location: | Ruaraka |
| Region: | Roysambu Division, Kasarani District, Nairobi. |
| Website (if applicable): | www.progressivevolunteers.or.ke |

- Type of applying organization

Please refer to the definitions in the Information Note.

| Is PV: | Yes | No |  | Yes | No |
| --- | --- | --- | --- | --- | --- |
| - non-governmental | X |  | - officially registered | X |  |
| - non-partisan | X |  |  |  |  |
| - not for-profit | X |  |  |  |  |
| When established (month, year): | May, 2007 |
| When registered (month, year): | August, 2008 |
| Type of registration: | Community Based Organization |
| Registration number: | CBO No 577 |

- Mission/structure of Progressive Volunteers

Progressive Volunteers is a community based organization founded in 2007 to meet the critical needs of young people living in Ruaraka and the sorrounding communities of Kasarani District, Nairobi. Objectives of the organization; Provide a platform for developing the skills of youth in order to help them become productive and responsible members of their communities. Engage in activities that will mitigate societal suffering: Capacity building. Economic empowerment. All-round awareness campaigns. Promote local development by effective management of volunteers and volunteer programmes. Support local-level peace and reconciliation initiatives. Identify and mobilize grassroots resource development. PV as a social community-based organization and already active in the community implementing programs and initiatives to assist and support the healthy and positive development of Kenya’s youth culture, has a credible organizational structure with a capable governance and competent management team to implement the project. Its volunteers are graduates from different disciplines, creating a pool of diverse and hence resourceful body. To date, PV has successfully conducted community outreach programs distributing health related Information, Education and Communication(IEC) materials and prevention commodities, conducted leadership and life skills development training forums targeting out of school youth, conducted community clean up exercises and offered micro enterprise development trainings on business idea generations, and simulation. We are committed to building on these accomplishments to improve the quality of life in the greater Ruaraka area.

- Project Title

First Aid Provisions in urban slums in Nairobi

- Summary

Progressive Volunteers is striving to improve self-reliance of individuals and urban communities to reduce their vulnerability, manage and mitigate impacts of natural and man made disasters in the urban slums of Nairobi, Kenya. The project empowers 200 people by training them on community-based first aid skills, preventive health care and environmental hygiene and purchasing of 320 first aid tool kits for some 50 learning institutions in Mathare, Kariobangi, Korogocho, and Baba Dogo communities.

- Project Duration

One cycle is expected to last for approximately six months, therefore in twelve months, double the number of people will have benefitted from the trainings.

- Project Area

The project to be implemented in Ruaraka, Kasarani District, Nairobi. In areas covering Mathare North, Mathare 4A, Baba Dogo, Kariadudu and neighboring Kariobangi and Korogocho communities.

- Required resources

$ 29,643

- Target groups

| Young men and women | X | Young parents | X |
| --- | --- | --- | --- |
| Children | X | Young single people with children | X |
| Elderly people | X | Disabled | X |
| Urban youth | X | Social centres | X |
| Youth who are out-of-school | X | Learning institutions | X |
| Youth with little or no formal education | X | Community in general | X |

- Problem Analysis

| Issues/challenges/needs | With dire poverty in the Nairobi urban slums, few people can afford basic healthcare services from the inaccessible, understaffed, very few and costly health centers. So many people when faced with emergencies in the house, school or in the community end up worsening the situation severely. For example, get hurt, disabled, prolonged illnesses and unnecessary deaths. The following issues affect these informal settlements Lack of trained and skilled first aiders to respond to emergencies. Inaccessible, understaffed, very few and costly health centers Lack of First Aid clubs in learning institutions. Lack of community preparedness for disasters |
| --- | --- |
| Importance of addressing proposed target group | Young people are the most energetic groups of people in the society whose stamina could be put into wasteful and wayward practices. It is therefore necessary to harness this energy into gainful means for themselves and the society at large as a way promoting rapid response to emergencies in the urban slums and eventually the entire country |
| How these issues and needs were identified | Members of the Progressive Volunteers (PV), who happen to come from within these communities, held several discussion sessions with the targetted youth groups, men and women on the streets and various learning institutions. Various intervention measures were collected in writing and community first aid training and educationwas found to be a conclusive, most urgent and concrete measure which would adress the rampant natural and man-made disasters. |

- Project Strategy :

| Key idea/solution | The project plans to carry out the following activities: Train and educate 200 Trainer of trainees on community-based first aid skills, preventive health care and environmental hygiene. The trainees to eventually train other community members in social centers and learning institutions. Purchasing of 320 first aid tool kits for 50 learning institutions in Mathare, Kariobangi, Korogocho and Baba Dogo communities. Groups of 4 trainees taking charge of the subsequent trainings at each learning institution and social centre. This will enable the empowered individuals to respond to daily emergencies in the inaccessible slums where health professionals are absent or overworked. |
| --- | --- |

- Implementation Plan :

| Key Activities :Recruitment of beneficiaries and Preparation of training materials Training of trainers of 200 people on community based first aid Establishment of first aid clubs in 50 learning instituions and purchase of 320 first aid tool kits First aid trainings in 50 learning institutions and 6 social centres Monthly follow up meetings Evaluation | Implementation time: October 2011 Novermber and December 2011 January 2012 February, march, April, and May 2012. October 2011- May 2012 June 2012 |
| --- | --- |

- Budget

| TOTAL GRANT REQUEST: |  |  |  | $ 29,643 |
| --- | --- | --- | --- | --- |
| item | Description | Calculation | Amount | Total ($) |
| Recruitment of beneficiaries and Preparation of training materials | Mobilization Printing of training manuals Flip charts Marker pens | 200@ 1$ 200@10$ 100@3$ 50@0.5$ | 200 2000 300 25 | 2,525 |
| Training of trainers of 200 people on community based first aid | Venue for trainings Refreshments and lunch Honorarium for trainers | 8 sessions@ 20$ 200@ 5$ 5@25$ | 160 1000 125 | 1,285 |
| Establishment of first aid clubs in 50 learning instituions | mobilization | 50@1$ | 50 | 50 |
| purchase of 320 first aid tool kits | First aid tool kits | 320@60.15$ | 19248 | 19,248 |
| First aid trainings in 50 learning institutions and 6 social centres of 20 participants each | Refreshments | 1120@3$ | 3360 | 3,360 |
| Monthly follow up meetings (Monitoring) | Refreshments | 7 meetings@ 10$ | 70 | 70 |
| Evaluation and Documentation |  |  |  | 500 |
| Administration- | Office supplies Volunteer allowances communication | lump sum 10 volunteers x 5 months x 40 USD 7 months x 15 USD | 500 2000 105 | 2,605 |
| Total |  |  |  | $29,643 |

- Key Project Outcomes

50 learning institutions from the informal settlement of Ruaraka, Nairobi shall be equiped with 320 first aid tool kits.

50 first aid clubs shall be established in the 50 learning institutions.

200 people(ToTs) trained on community based first aid skills, preventive health care and environmental hygiene. The ToTs to carry on with subsequent trainings.

Over 1000 school going students from the learning institutions trained and educated on basic first aid skills

Empowered individuals and communities trained and educated in order to reduce, manage and mitigate impacts of natural and man-made disasters, emergencies within informal settlements.

# Text boxes

# Part A:      PROGRESSIVE vOLUNTEERS Information

# Part B:      Project Overview

# Part C:      BACKGOUND AND JUSTIFICATION

# Part D:    PROJECT STRATEGY AND PLAN